## 9-28-23
UPDATED: 9/28/23
PROJECT NAME | LOCATION | DESCRIPTION | AGENCY/ CONTRACTOR/ DEVELOPER | SCHEDULED START | SCHEDULED FINISH | IMPACTS | UPDATES
Trash Enclosure Livermore Village Parking Garage: Phase 1 | Livermore Village Parking Lot | Construct Trash Enclosure and re-pave surface adajcent surface lot in preparation for L-Street Garage construction | WestCal | August 2022 | COMPLETE | No further impacts expected at this time | COL Building and LPFD signed off for occupancy City currently has provided business owners keys to access enlosure. Garbage bins remain outside the enclosure until interior protection is installed as requested by Livermore Sanitation
Trash Enclosure Livermore Village Parking Garage: Phase 1 SURFACE IMPROVEMENTS | Livermore Village Parking Lot | Construct Trash Enclosure and re-pave surface adajcent surface lot in preparation for L-Street Garage construction | WestCal | 4/5/23 | COMPLETE | No further impacts expected at this time | Work Complete No further exterior impacts around the trash enclosure structure expected.
L-Street Garage Livermore Village Parking Garage: Phase 2 | Livermore Village Veterans Way and S L Street | Construct new L-Street Garage on the corner of S L Street and Veterans Way | Zovich | 4/17/23 | Fall of 2024 | Closure of SW corner of Livermore Village (Garage Location) , west half of veterans way including north and south walkways (West of K St), Closure of East sidewalk of S L Street - south of Veterans Way One way traffic on S K Street aisle through Veterans way for JT work | Contractor still mainly working on building footings and the joint trench. S K Street aisle currently only allows ONE WAY traffic through Veterans way to allow the construction of the Joint Trench. Detour signs are posted to help re-direct vehicles. Both directions of the S K St. aisle is scheduled to be re-opened mid next week - Contractor had issues with locating existing conduits from the previous project that extended the closure time. Contractor closed the sidewalk on the east side of S L Street - Pedestrians are detoured to the west sidewalk at Railroad and First St. Flashing beacon and crosswalk by Veterans way will be installed soon.
Livermore Legacy NORTH | First Street / S L Street / Railroad Ave / S M Street | Livermore Legacy Apartments Frontage Improvements | Legacy / SBI | 2021 | Late October 2023 | Lane closures on RR Ave and S L Street as needed for any corrective or onsite work | Flex zone parking on north side of First St. OPEN to the public All sidewalks around the developement are OPEN to the public Legacy contractior mainly working on offsite punchlist items
2021 Resurfacing Project | Citywide In Downtown: (S Livermore/4th/East) | Overlay AC Roadway and update ADA Ramps | MCK | 2023-04-10 | 8/11/23 | No further impacts in downtown area expected at this time | Contractor completed pavement rehabilitaion (base repair, overlay, and striping) on S Livermore Ave. and East/4th
2021 Slurry Seal Project | Citywide In Downtown: (S Livermore/4th/East) | Slurry Seal Roadway and update ADA Ramps | Pavement Coatings Co. | 6/12/23 | 11/1/23 | Road Closure and Lane Closure around the area of the S Livermore Ave. & 5th St intersection (Tentative mid-late OCTOBER) | Slurry Seal short section of S H Street between S Livermore Ave and 5th Street Slurry Seal - Mid October
Comcast Encroachment Permit | Livermore Village Parking Lot | Install service laterals for downtown establishements (north side) | Comcast / Sefnco | 5/8/23 | TBD | No scheduled work at this time | Installation of service lateral installation to businesses - night work No work is scheduled at this time Also working in private property area (Madden)
Encroachment Permit No. EN230004 AT&T | First Street / S J Street | Replace/Splice Fiber Cable | AT&T | TBD | TBD | Loss of Parking Spaces on First Street and S J Street | No Updates this week Permit Issued - Waiting for AT&T to schedule pre-con and provide tentative start date.
Encroachment Permit No. EN230093 AT&T | Railoroad Ave. East of S Livermore Ave. | Traffic Control to access vaults | AT&T | TBD | TBD | Right Lane closure on WB Railroad Ave. | No Updates this week Permit Issued - Waiting for AT&T to schedule pre-con and provide tentative start date.
Encroachment Permit No. EN230095 AT&T | First to Second St. McLeod to Maple | Traffic Control to access pole & vaults | AT&T | TBD | TBD | Work will occupy 4-6 parking spaces at a time between 1st & 2nd /McLeod & Maple | No Updates this week Permit Issued - Waiting for AT&T to schedule pre-con and provide tentative start date.
Encroachment Permit No. EN230101 Mill Springs Apartments | Railoroad Ave. West of S L Street | Planting along frontage of Apartment Complex | A Plus Trees | TBD | TBD | Right Lane closure on EB Railroad Ave. | No Updates this week Start date TBD - Contractor to schedule pre-con with assigned inspector
Encroachment Permit No. EN230253 CalWater | N L Street S 4th Street to S 6th Street | Water main replacement | CalWater | 8/29/23 | Mid October | Intermittent road and lane closure of S L Street from 6Th St. to 4th St. | Water main replacement work service transfer to new line completed CWS will be working on pavement restoration and striping next week (Monday 10/2/23 to Tuesday 10/3/23)
NEW Encroachment Permit No. EN230137 Comcast | 2044 First St (Behind Thirsty Agave) | Install service lateral to Thirsty Agave Building | Comcast / Sefnco | 10/2/23 | 10/6/23 | Working next to new sidewalk behind First St. businesses - No impacts expected | Comcast intends to bore underneath the new sidewalk behind the First St. business to run a service line to the Thirsty Agave building. Tentative Start Date 10/6/23

## 9-5-23
UPDATED: 9/5/23
PROJECT NAME | LOCATION | DESCRIPTION | AGENCY/ CONTRACTOR/ DEVELOPER | SCHEDULED START | SCHEDULED FINISH | IMPACTS | UPDATES
Trash Enclosure Livermore Village Parking Garage: Phase 1 | Livermore Village Parking Lot | Construct Trash Enclosure and re-pave surface adajcent surface lot in preparation for L-Street Garage construction | WestCal | August 2022 | Late Aug 2023 | No further impacts expected at this time | Construction fence around the trash enclosure structure has been taken down. Fire Department sign off and occupancy pending replacement of potential defective valve. City currently working with business owners regarding access and usage of the enlosure. Once occupancy is granted, contractor will remove plywood from temporary trash area, garbage bins will be stored inside the enclosure, and designated ADA parking stalls will be available.
Trash Enclosure Livermore Village Parking Garage: Phase 1 SURFACE IMPROVEMENTS | Livermore Village Parking Lot | Construct Trash Enclosure and re-pave surface adajcent surface lot in preparation for L-Street Garage construction | WestCal | 4/5/23 | Late Aug 2023 | No further impacts expected at this time | Corrective Work to meet ADA requirements are complete. No further exterior impacts around the trash enclosure structure expected.
L-Street Garage Livermore Village Parking Garage: Phase 2 | Livermore Village Veterans Way and S L Street | Construct new L-Street Garage on the corner of S L Street and Veterans Way | Zovich | 4/17/23 | Fall of 2024 | Closure of SW corner of Livermore Village (Garage Location) , west half of veterans way including north and south walkways (West of K St), Closure of East sidewalk of S L Street - south of Veterans Way One way traffic on S K Street aisle through Veterans way for JT work | Contractor mainly working building footings and the joint trench. S K Street aisle currently only allows ONE WAY traffic through Veterans way to allow the construction of the Joint Trench. Detour signs are posted to help re-direct vehicles. Both directions of the S K St. aisle is scheduled to be re-opened on 9/26/23 - Pending PGE approval. Contractor completed and OPENED the new sidewalk on the south side of the garage on 8/24/23. Contractor scheduled to close the sidewalk on the east side of S L Street on 9/10/23 - There is an active detour route through the parking area, additional detour will be in place to redirect pedestrians to west side of S L St. City has also provided contractor with updated plans for the crosswalk and pedestrian beacons on S L St.
Livermore Legacy NORTH | First Street / S L Street / Railroad Ave / S M Street | Livermore Legacy Apartments Frontage Improvements | Legacy / SBI | 2021 | LATE Aug 2023 | Lane closures on RR Ave and S L Street as needed for any corrective or onsite work | Flex zone parking on north side of First St. Open to the public All sidewalks around the developement will be OPEN to the public Legacy contractior mainly working on offsite punchlist items Contractor finished overlaying and re-striping Railroad Ave. Lights on Railroad Ave and S L Street are operational. City continues to work with PGE to re-connect pedestal on S L Street that powers all the offsite lighting on North side of First St. and S M Street
2021 Resurfacing Project | Citywide In Downtown: (S Livermore/4th/East) | Overlay AC Roadway and update ADA Ramps | MCK | 2023-04-10 | 8/11/23 | No further impacts in downtown area expected at this time | Contractor completed pavement rehabilitaion (base repair, overlay, and striping) on S Livermore Ave. and East/4th
2021 Slurry Seal Project | Citywide In Downtown: (S Livermore/4th/East) | Slurry Seal Roadway and update ADA Ramps | Pavement Coatings Co. | 6/12/23 | 11/1/23 | Road Closure, Lane Closure, and Detours & Pedestrian Detours at the intersection of S Livermore Ave. & 5th (Tentative mid-late SEPTEMBER) | Slurry Seal short section of S H Street between S Livermore Ave and 5th Street Concrete Ramps - Mid Sept Slurry Seal - Late Sept
Comcast Encroachment Permit | Livermore Village Parking Lot | Install service laterals for downtown establishements (north side) | Comcast / Sefnco | 5/8/23 | TBD | No scheduled work at this time | Installation of service lateral installation to businesses - night work No work is scheduled at this time Also working in private property area (Madden)
Encroachment Permit No. EN220589 CalWater | 2nd Street between K and L; K Street between 1st and 3rd; J Street between 1st and 3rd | Water main replacement | CalWater | 4/17/23 | COMPLETE | Work COMPLETED | Work COMPLETED
Encroachment Permit No. EN230112 Comcast | S L Street (from 3rd to 5th) | Bore new line and install vaults | Comcast / Sefnco | 4/12/23 | COMPLETE | Work COMPLETED | Work COMPLETED
Encroachment Permit No. EN230004 AT&T | First Street / S J Street | Replace/Splice Fiber Cable | AT&T | TBD | TBD | Loss of Parking Spaces on First Street and S J Street | No Updates this week Permit Issued - Waiting for AT&T to schedule pre-con and provide tentative start date.
Encroachment Permit No. EN230093 AT&T | Railoroad Ave. East of S Livermore Ave. | Traffic Control to access vaults | AT&T | TBD | TBD | Right Lane closure on WB Railroad Ave. | No Updates this week Permit Issued - Waiting for AT&T to schedule pre-con and provide tentative start date.
Encroachment Permit No. EN230095 AT&T | First to Second St. McLeod to Maple | Traffic Control to access pole & vaults | AT&T | TBD | TBD | Work will occupy 4-6 parking spaces at a time between 1st & 2nd /McLeod & Maple | No Updates this week Permit Issued - Waiting for AT&T to schedule pre-con and provide tentative start date.
Encroachment Permit No. EN230101 Mill Springs Apartments | Railoroad Ave. West of S L Street | Planting along frontage of Apartment Complex | A Plus Trees | TBD | TBD | Right Lane closure on EB Railroad Ave. | No Updates this week Start date TBD - Contractor to schedule pre-con with assigned inspector
Encroachment Permit No. EN230172 USPS | S Livermore Ave. In front of Post Office | Remove and Replace Sidewalk | Goebel Construction | 5/25/23 | 5/26/23 | Work COMPLETED | Work COMPLETED
Encroachment Permit No. EN220452 CalWater | N P Street Locust Street N K Street | Water main replacement | CalWater |  | 6/23/23 | Work COMPLETED | Work COMPLETED
NEW Encroachment Permit No. EN230253 CalWater | N L Street S 4th Street to S 6th Street | Water main replacement | CalWater | 8/29/23 | 9/15/23 | Intermittent road and lane closure of S L Street from 6Th St. to 4th St. | CWS working on Water main replacement Residents and businesses have been notified, including scheduled service shut down. Service shutdown will be approximately 8hrs long - CWS has taken additional measures to avoid service shutdown to some residents and business. Follow up notification will be provided closer to shut down date

## 8-2-23
UPDATED: 8/2/23
PROJECT NAME | LOCATION | DESCRIPTION | AGENCY/ CONTRACTOR/ DEVELOPER | SCHEDULED START | SCHEDULED FINISH | IMPACTS | UPDATES
Trash Enclosure Livermore Village Parking Garage: Phase 1 | Livermore Village Parking Lot | Construct Trash Enclosure and re-pave surface adajcent surface lot in preparation for L-Street Garage construction | WestCal | August 2022 | Late Aug 2023 | Construction fencing around structure and some adjacent parking spaces | Currently working on punchlist items and ADA corrections Removal of construction fence TBD
Trash Enclosure Livermore Village Parking Garage: Phase 1 SURFACE IMPROVEMENTS | Livermore Village Parking Lot | Construct Trash Enclosure and re-pave surface adajcent surface lot in preparation for L-Street Garage construction | WestCal | 4/5/23 | Late Aug 2023 | Closure of ADA parking spaces for ADA correction work | Corrective Work: Working on repaving ADA parking spaces to meet ADA requirements
L-Street Garage Livermore Village Parking Garage: Phase 2 | Livermore Village Veterans Way and S L Street | Construct new L-Street Garage on the corner of S L Street and Veterans Way | Zovich | 4/17/23 | Fall of 2024 | Closure of SW corner of Livermore Village (Garage Location) , west half of veterans way including north and south walkways (West of K St), 10-day Closure of designated pedestrian pathway on the south side of the project limits Closure of East sidewalk of S L Street - south of Veterans Way (TBD) When the contractor resumes work on Joint Trench on S K Street, they will have to narrowed down the delivery route on S K Street - Contractor installed steel plates over trench to provide more room for delivery trucks | Contractor mainly working on off hauling contaminated top soil from the site this week. This will be follwed by rough grading for the building pad and compaction for certification. Contractor will begin construction of the new sidewalk on the south side of the garage on 8/14/23. The designated pedestrian pathway behind Murphy's paw/Caratti jewlers will be unavailable for 10 days Downtown businesses will be given advance notification Joint Trench work on hold. *Waiting on PGE inspection of trench bedding to proceed with conduit installation - Inspection tentatively scheduled for early Aug. Temporary loading zone on First Street in place (between Murphy's Paw and Caratti jewelers) Delivery route and loading zone behind downtown businesses in place.
Livermore Legacy NORTH | First Street / S L Street / Railroad Ave / S M Street | Livermore Legacy Apartments Frontage Improvements | Legacy / SBI | 2021 | LATE Aug 2023 | Lane closures on EB RR Ave for overlay work Temporary sidewalk closures on RR and 1st for sidewalk corrective work | Legacy Building A and B granted Temporary Occupancy Flex zone parking on north side of First St. Open to the public All sidewalks around the developement will be OPEN to the public by 8/11/23 Legacy contractior mainly working on offsite punchlist items -Demo section of sidewalk at the corner of 1st and S L to install roof drains week of 8/7/23 -Demo section of sidewalk on RR Ave to replace damaged sidewalk week of 8/7/23 Legacy contractor will be working on connecting S L Street lighting to power source on RR ave. City continues to work with PGE to re-connect pedestal on S L Street that powers all the offsite lighting on North side of First St. and S M Street Legacy contractor still working on completing wiring for all associated lighting. Legacy contractor completed repair of sidewalk and driveway in front of Purpose Built (along First St.)
2021 Resurfacing Project | Citywide In Downtown: (S Livermore/4th/East) | Overlay AC Roadway and update ADA Ramps | MCK | 2023-04-10 | 8/11/23 | Road Closures, Lane Closures, and Detours & Pedestrian Detours at the intersection of S Livermore Ave. & East/4th | Start of pavement rehabilitaion (base repair, overlay, and striping) on S Livermore Ave. and East/4th Aug 8 to Aug 11 Contractor has posted advance notification on both directions of S Livermore Ave.
2021 Slurry Seal Project | Citywide In Downtown: (S Livermore/4th/East) | Slurry Seal Roadway and update ADA Ramps | Pavement Coatings Co. | 6/12/23 | 11/1/23 | Road Closure, Lane Closure, and Detours & Pedestrian Detours at the intersection of S Livermore Ave. & 5th (Tentative mid-late August) | Slurry Seal short section of S H Street between S Livermore Ave and 5th Street - (Tentative mid-late August) Notice to Proceed issued 6/12/23
Comcast Encroachment Permit | Livermore Village Parking Lot | Install service laterals for downtown establishements (north side) | Comcast / Sefnco | 5/8/23 | TBD | Closure of pedestrian pathway behind downtown businesses during night work | Continue working on service lateral installation to businesses - will be working on nights along pedestrian pathway behind downtown businesses Also working in private property area (Madden)
Encroachment Permit No. EN220589 CalWater | 2nd Street between K and L; K Street between 1st and 3rd; J Street between 1st and 3rd | Water main replacement | CalWater | 4/17/23 | COMPLETE | Work COMPLETED | Work COMPLETED
Encroachment Permit No. EN230112 Comcast | S L Street (from 3rd to 5th) | Bore new line and install vaults | Comcast / Sefnco | 4/12/23 | 5/19/23 | Work COMPLETED | Restoration complete Final inspection pending
Encroachment Permit No. EN230004 AT&T | First Street / S J Street | Replace/Splice Fiber Cable | AT&T | TBD | TBD | Loss of Parking Spaces on First Street and S J Street | No Updates this week Permit Issued - Waiting for AT&T to schedule pre-con and provide tentative start date.
Encroachment Permit No. EN230093 AT&T | Railoroad Ave. East of S Livermore Ave. | Traffic Control to access vaults | AT&T | TBD | TBD | Right Lane closure on WB Railroad Ave. | No Updates this week Permit Issued - Waiting for AT&T to schedule pre-con and provide tentative start date.
Encroachment Permit No. EN230095 AT&T | First to Second St. McLeod to Maple | Traffic Control to access pole & vaults | AT&T | TBD | TBD | Work will occupy 4-6 parking spaces at a time between 1st & 2nd /McLeod & Maple | No Updates this week Permit Issued - Waiting for AT&T to schedule pre-con and provide tentative start date.
Encroachment Permit No. EN230101 Mill Springs Apartments | Railoroad Ave. West of S L Street | Planting along frontage of Apartment Complex | A Plus Trees | TBD | TBD | Right Lane closure on EB Railroad Ave. | No Updates this week Start date TBD - Contractor to schedule pre-con with assigned inspector
Encroachment Permit No. EN230172 USPS | S Livermore Ave. In front of Post Office | Remove and Replace Sidewalk | Goebel Construction | 5/25/23 | 5/26/23 | Work COMPLETED | Work COMPLETED
Encroachment Permit No. EN220452 CalWater | N P Street Locust Street N K Street | Water main replacement | CalWater |  | 6/23/23 | Work COMPLETED | Work COMPLETED

## 7-6-23
UPDATED: 7/6/23
PROJECT NAME | LOCATION | DESCRIPTION | AGENCY/ CONTRACTOR/ DEVELOPER | SCHEDULED START | SCHEDULED FINISH | IMPACTS | UPDATES
Trash Enclosure Livermore Village Parking Garage: Phase 1 | Livermore Village Parking Lot | Construct Trash Enclosure and re-pave surface adajcent surface lot in preparation for L-Street Garage construction | WestCal | August 2022 | Mid July 2023 | Construction fencing around structure and some adjacent parking spaces | Contractor completed roofing, roll up doors, and gate installation. Currently working on punchlist items Removal of construction fence scheduled Mid-July
Trash Enclosure Livermore Village Parking Garage: Phase 1 SURFACE IMPROVEMENTS | Livermore Village Parking Lot | Construct Trash Enclosure and re-pave surface adajcent surface lot in preparation for L-Street Garage construction | WestCal | 4/5/23 | Completed | Loss of 1 or 2 parking spaces and short term for any corrective work | Surface improvements complete Construction fencing only around structure work Working on minor corrective items
L-Street Garage Livermore Village Parking Garage: Phase 2 | Livermore Village Veterans Way and S L Street | Construct new L-Street Garage on the corner of S L Street and Veterans Way | Zovich | 4/17/23 | Fall of 2024 | Closure of SW corner of Livermore Village (Garage Location) , west half of veterans way including north and south walkways (West of K St), Closure of East sidewalk of S L Street - south of Veterans Way (TBD) JT work on S K Street narrowed down the delivery route on S K Street - Contractor installed steel plates over trench to provide more room for delivery trucks | Contractor mainly working on constructing building pad. Once certified, they will start construction of building footings. *Contractor encountered multiple underground tanks during pad excavation. City environmental consultant worked with LPFD with the removal. Additional testing and cleanup required at one of the locations - in progress Continue work on Joint Trench that runs along the north walkway on Veterans way and down S K Street (south of gravel area) *Waiting on PGE inspection of trench bedding to proceed with conduit installation - Inspection tentatively scheduled for early Aug. Staff will be reaching out to PGE to try and move up inspection date. Designated pedestrian pathway between First St. and parking area in place - Located on the south side of the project Temporary loading zone on First Street in place (between Murphy's Paw and Caratti jewelers) Delivery route and loading zone behind downtown businesses in place.
Livermore Legacy NORTH | First Street / S L Street / Railroad Ave / S M Street | Livermore Legacy Apartments Frontage Improvements | Legacy / SBI | 2021 | LATE July 2023 | Regular RIGHT LANE Closure on EB Railroad Ave. until late July for onsite work Lane closures on both directions of RR Ave for Sewer connection work | Legacy Building A (Buildng along First St.) granted Temporary Occupancy (TCO) on 6/13/23 Sidewalk on S L Street, First Street, and S M Street OPEN to the public *Sidewalk on RR Ave. scheduled to be re-opened in late June installation of parking markers for flex zone area scheduled for early next week - Flex zone area parking to be opened shortly after. *Areas around trellises and tree wells are temporarily filled with decomposed granite to allow use of parking area - contractor to pour concrete once specified uplights are installed Single post trellises complete. Currently working on the 4-post trellis next to S M Street *Legacy soon to begin working on installing new Sanitary Sewer lateral on RR Ave
2021 Resurfacing Project | Citywide In Downtown: (S Livermore/4th/East) | Overlay AC Roadway and update ADA Ramps | MCK | 2023-04-10 | 8/4/23 | Road Closures, Lane Closures, and Detours & Pedestrian Detours at the intersection of S Livermore Ave. & East/4th | Start of pavement rehabilitaion (base repair, overlay, and striping) tentative for LATE JULY Contractor will be providing 72 Hrs notification to affected residents, establishments, and buisnesses
2021 Slurry Seal Project | Citywide In Downtown: (S Livermore/4th/East) | Slurry Seal Roadway and update ADA Ramps | Pavement Coatings Co. | 6/12/23 | 11/1/23 | Road Closure, Lane Closure, and Detours & Pedestrian Detours at the intersection of S Livermore Ave. & 5th (Tentative mid-late August) | Slurry Seal short section of S H Street between S Livermore Ave and 5th Street - (Tentative mid-late August) Notice to Proceed issued 6/12/23
Comcast Encroachment Permit | Livermore Village Parking Lot | Install service laterals for downtown establishements (north side) | Comcast / Sefnco | 5/8/23 | TBD | No additional impact - work will be inside L-Street Garage fenced area OR private property | Continue working on service lateral installation to businesses behind L-Street Garage construction fence. Also working in private property area (Madden)
Encroachment Permit No. EN220589 CalWater | 2nd Street between K and L; K Street between 1st and 3rd; J Street between 1st and 3rd | Water main replacement | CalWater | 4/17/23 | 6/27/23 | Lane closures and loss of parking spaces on 2nd street between S L St. and S J St. | CWS Completed slurry sealing 2nd street and installation of pavement markings CWS needs to raise 2 utility covers - to be scheduled
Encroachment Permit No. EN230112 Comcast | S L Street (from 3rd to 5th) | Bore new line and install vaults | Comcast / Sefnco | 4/12/23 | 5/19/23 | Work COMPLETED | Restoration complete Final inspection pending
Encroachment Permit No. EN230004 AT&T | First Street / S J Street | Replace/Splice Fiber Cable | AT&T | TBD | TBD | Loss of Parking Spaces on First Street and S J Street | No Updates this week Permit Issued - Waiting for AT&T to schedule pre-con and provide tentative start date.
Encroachment Permit No. EN230093 AT&T | Railoroad Ave. East of S Livermore Ave. | Traffic Control to access vaults | AT&T | TBD | TBD | Right Lane closure on WB Railroad Ave. | No Updates this week Permit Issued - Waiting for AT&T to schedule pre-con and provide tentative start date.
Encroachment Permit No. EN230095 AT&T | First to Second St. McLeod to Maple | Traffic Control to access pole & vaults | AT&T | TBD | TBD | Work will occupy 4-6 parking spaces at a time between 1st & 2nd /McLeod & Maple | No Updates this week Permit Issued - Waiting for AT&T to schedule pre-con and provide tentative start date.
Encroachment Permit No. EN230101 Mill Springs Apartments | Railoroad Ave. West of S L Street | Planting along frontage of Apartment Complex | A Plus Trees | TBD | TBD | Right Lane closure on EB Railroad Ave. | No Updates this week Start date TBD - Contractor to schedule pre-con with assigned inspector
Encroachment Permit No. EN230172 USPS | S Livermore Ave. In front of Post Office | Remove and Replace Sidewalk | Goebel Construction | 5/25/23 | 5/26/23 | Work COMPLETED | Work COMPLETED
Encroachment Permit No. EN220452 CalWater | N P Street Locust Street N K Street | Water main replacement | CalWater |  | 6/23/23 | Work COMPLETED | Work COMPLETED

## 6-13-23
UPDATED: 6/13/23
PROJECT NAME | LOCATION | DESCRIPTION | AGENCY/ CONTRACTOR/ DEVELOPER | SCHEDULED START | SCHEDULED FINISH | IMPACTS | UPDATES
Trash Enclosure Livermore Village Parking Garage: Phase 1 | Livermore Village Parking Lot | Construct Trash Enclosure and re-pave surface adajcent surface lot in preparation for L-Street Garage construction | WestCal | August 2022 | Late June 2023 | Construction fencing around structure and some adjacent parking spaces | Contractor completed exterior improvements. Continues to work on roof installation and electrical. Installation of roll up doors and occupancy expected mid next week Removal of construction fence scheduled before end of June
Trash Enclosure Livermore Village Parking Garage: Phase 1 SURFACE IMPROVEMENTS | Livermore Village Parking Lot | Construct Trash Enclosure and re-pave surface adajcent surface lot in preparation for L-Street Garage construction | WestCal | 4/5/23 | Completed | Loss of 1 or 2 parking spaces and short term for any corrective work | Surface improvements complete Construction fencing only around structure work Working on minor corrective items
L-Street Garage Livermore Village Parking Garage: Phase 2 | Livermore Village Veterans Way and S L Street | Construct new L-Street Garage on the corner of S L Street and Veterans Way | Zovich | 4/17/23 | Fall of 2024 | Closure of SW corner of Livermore Village (Garage Location) , west half of veterans way including north and south walkways (West of K St), Closure of East sidewalk of S L Street - south of Veterans Way (Tentative for first week of July) JT work on S K Street will narrow down the delivery route on S K Street - Contractor will install steel plates over trench to provide more room for delivery trucks | Contractor fenced off garage area and west half of Veterans way Detour and directional signs in place Staff continues to evaluate signage and layout and will make adjustments as necessary for public safety and ease of use -Contractor completed remediation work (excavation of contaminated material) - wating for paperwork to be processed to be able to off haul. -Contractor working on over-excavation for building footings -Continue work on Joint Trench along the north walkway of Veterans way. They are scheduled to start the section of JT on S K Street next week. *Printed screen around construction fence installed *Ground Breaking Ceremony Scheduled Friday 6/16 Designated pedestrian pathway on the south side of the project in place (Located behind murphy's paw to First St. Ale house) Contractor placed steel plates to provide pedestrians flat surface walkway Delivery route and loading zone behind downtown businesses in place. Crosswalk across S L Street tentatively scheduled for first week of July - Waiting on flashing beacon installation for safety
Livermore Legacy NORTH | First Street / S L Street / Railroad Ave / S M Street | Livermore Legacy Apartments Frontage Improvements | Legacy / SBI | 2021 | LATE July 2023 | Regular RIGHT LANE Closure on EB Railroad Ave. until June for onsite work Lane closures on both directions of RR Ave starting this week for Sewer work Same day lane closures on S L Street and First St. as needed | Legacy Building A (Buildng along First St.) granted Temporary Occupancy (TCO) - Today 6/13/23 *Pouring remaining sections of blue stone sidewalk along first street today (6/13/23) - Sidewalk on First Street to be open to public Thursday 6/15 *S L Street Sidewalk (west side) open to public today 6/13 - including ramps on S L and First St. *Flex Zone parking area on First St. shall remain closed until contractor completes installation of parking markers and temporarily backfilling unpaved areas with decompost granite - tenative to be open early next week - Flex zone area will be delineated closed until safe to open. *Legacy to provide power to street lights on First St. and M St. temporarily until damaged pedestal on S L St. is re-energized by PGE - Street lights will be on by the end of this week 6/16 *Legacy working on trellis this week and next week *S M St re-opened - pavement marking tomorrow 6/14 *Legacy will begin working on installing new Sanitary Sewer line on RR Ave - Starts tomorrow 6/14 and will continue through next week. (See impacts)
2021 Resurfacing Project | Citywide In Downtown: (S Livermore/4th/East) | Overlay AC Roadway and update ADA Ramps | MCK | 2023-04-10 | 8/4/23 | Road Closures, Lane Closures, and Detours & Pedestrian Detours at the intersection of S Livermore Ave. & East/4th | Start of pavement rehabilitaion (base repair, overlay, and striping) tentative for LATE JULY Contractor will be providing 72 Hrs notification to affected residents, establishments, and buisnesses
2021 Slurry Seal Project | Citywide In Downtown: (S Livermore/4th/East) | Slurry Seal Roadway and update ADA Ramps | Pavement Coatings Co. | 6/12/23 | 11/1/23 | Road Closure, Lane Closure, and Detours & Pedestrian Detours at the intersection of S Livermore Ave. & 5th (Tentative mid-late August) | Slurry Seal short section of S H Street between S Livermore Ave and 5th Street - (Tentative mid-late August) Notice to Proceed issued 6/12/23
Comcast Encroachment Permit | Livermore Village Parking Lot | Install service laterals for downtown establishements (north side) | Comcast / Sefnco | 5/8/23 | TBD | No additional impact - work will be inside L-Street Garage fenced area | No tentative start/resume date at this time
Encroachment Permit No. EN220589 CalWater | 2nd Street between K and L; K Street between 1st and 3rd; J Street between 1st and 3rd | Water main replacement | CalWater | 4/17/23 | 6/27/23 | (Pending approval for next week) Daytime lane closure on 2nd street between S J St. and S L St. (will close one half of road at a time) 1 day for slurry seal 1 day for striping Loss of parking spaces within closure areas | CWS Completed trench pavement restoration. Slurry sealing of 2nd St between S J St. and S L St. tentative for Monday 6/18/23 Notifications and NO PARKING signs will be posted 72 hrs in advance Re-striping tenative for Monday 6/26/23
Encroachment Permit No. EN230112 Comcast | S L Street (from 3rd to 5th) | Bore new line and install vaults | Comcast / Sefnco | 4/12/23 | 5/19/23 | Work COMPLETED | Restoration complete Final inspection pending
Encroachment Permit No. EN230004 AT&T | First Street / S J Street | Replace/Splice Fiber Cable | AT&T | TBD | TBD | Loss of Parking Spaces on First Street and S J Street | No Updates this week Permit Issued - Waiting for AT&T to schedule pre-con and provide tentative start date.
Encroachment Permit No. EN230093 AT&T | Railoroad Ave. East of S Livermore Ave. | Traffic Control to access vaults | AT&T | TBD | TBD | Right Lane closure on WB Railroad Ave. | No Updates this week Permit Issued - Waiting for AT&T to schedule pre-con and provide tentative start date.
Encroachment Permit No. EN230095 AT&T | First to Second St. McLeod to Maple | Traffic Control to access pole & vaults | AT&T | TBD | TBD | Work will occupy 4-6 parking spaces at a time between 1st & 2nd /McLeod & Maple | No Updates this week Permit Issued - Waiting for AT&T to schedule pre-con and provide tentative start date.
Encroachment Permit No. EN230101 Mill Springs Apartments | Railoroad Ave. West of S L Street | Planting along frontage of Apartment Complex | A Plus Trees | TBD | TBD | Right Lane closure on EB Railroad Ave. | No Updates this week Start date TBD - Contractor to schedule pre-con with assigned inspector
Encroachment Permit No. EN230172 USPS | S Livermore Ave. In front of Post Office | Remove and Replace Sidewalk | Goebel Construction | 5/25/23 | 5/26/23 | Work COMPLETED | Work COMPLETED
Encroachment Permit No. EN220452 CalWater | N P Street Locust Street N K Street | Water main replacement | CalWater |  | 6/23/23 | Lane closure on Locust to install STOP bar | All work complete except for one STOP bar - Temp STOP bar in place - will be installed along with striping of down town slurry seal work - See permit EN220589 notes

## 5-25-23
UPDATED: 5/25/23
PROJECT NAME | LOCATION | DESCRIPTION | AGENCY/ CONTRACTOR/ DEVELOPER | SCHEDULED START | SCHEDULED FINISH | IMPACTS | UPDATES
Trash Enclosure Livermore Village Parking Garage: Phase 1 | Livermore Village Parking Lot | Construct Trash Enclosure and re-pave surface adajcent surface lot in preparation for L-Street Garage construction | WestCal | August 2022 | Late May 2023 | Pedestrian Detours Loss of Parking Spaces | Contractor completed paving inside previously fenced area. Construction fence has been moved to only enclose outside permimeter of building Will be installing roof tiles, DEFS (Direct-applied Exterior Finish), and light poles this week Projected still expected to be substantially complete by LATE MAY 2023
Trash Enclosure Livermore Village Parking Garage: Phase 1 SURFACE IMPROVEMENTS | Livermore Village Parking Lot | Construct Trash Enclosure and re-pave surface adajcent surface lot in preparation for L-Street Garage construction | WestCal | 4/5/23 | Late May 2023 | Loss of 1 or 2 parking spaces and short term closure for striping | Paving and Striping completed Construction fences moved back to re-open parking area improvements Contractor plans to installing light poles this week
L-Street Garage Livermore Village Parking Garage: Phase 2 | Livermore Village Veterans Way and S L Street | Construct new L-Street Garage on the corner of S L Street and Veterans Way | Zovich | 4/17/23 | Fall of 2024 | Closure of SW corner of Livermore Village (Garage Location) , west half of veterans way including north and south walkways (West of K St), Closure of East sidewalk of S L Street (south of Veterans Way) *Closure of EAST sidewalk on S L Street dependent on Installation of L Street Crosswalk & flashing beacon, and opening of S L Street WEST Walkway by Legacy | Contractor completed the installation of Vapor Extraction System on the north side of Livermore Village and the rehabilitation of the gravel area of parking lot Contractor fenced off garage area and west half of Veterans way to begin demolition and rough grading work. Designated pedestrian pathway on the south side of the project in place (Located behind murphy's paw to First St. Ale house) Staff is currently working with contractor to provide a paved pathway for added safety and convinience Delivery route and loading zone behind downtown businesses in place. Staff continues to work with contractor to improve Directional and Parking signage around Livermore Village Crosswalk across S L Street tentatively scheduled for first week of June - Waiting on update regarding flashing beacon availability. East sidewalk on S L Street will be closed upon installation (Livermore Legacy expected to have the west sidewalk open by that time - See Legacy updates)
Livermore Legacy NORTH | First Street / S L Street / Railroad Ave / S M Street | Livermore Legacy Apartments Frontage Improvements | Legacy / SBI | 2021 | LATE July 2023 | Lane closures on S L Street and North side of first Street for 2 days to pave/overlay streets. -(S L Street) Traffic will be shifted to one side of the street allow grinding and paving -(WB 1st Street) will be closed and detoured to allow grinding and paving - Closure will be in the morning and re-opened before business hours (11am) Regular RIGHT LANE Closure on EB Railroad Ave. until June Full closure of S M Street for construction of new pavement Lane closure on First Streeet on Friday 5/12/23 for S M Street Paving | Legacy has pushed back Building A (Building along First St) Occupancy target date to June 8, 2023 Contractor continue to work on First Street imrpovements. The following were recently completed -Pour blue stone concrete sidewalk and valley gutter -Installed foundations for trellises The following will occur this following week: -Pour concrete for flex zone area - (Pending favorable shrinkage test) -Pour concrete for remaining ramps and curbs Legacy tenatively scheduled to pave/overlay S L Street and north half of First street in NEXT WEEK Starting 5/30 - This also includes top lift of S M Street (See impacts) S L Street WEST sidewalk still expected to open by End of May - They will be placing the remaining concrete sidewalk to allow pedestrians to cross from NW corner to SW corner of the intersection of S L and First St. S M Street (north of First St) still closed. Paving of Asphalt concrete BASE lift for S M Street scheduled for 5/12/23 Re-opening of Sidewalk on RR Ave pushed back to early June due to an onsite corrective work
2021 Resurfacing Project | Citywide In Downtown: (S Livermore/4th/East) | Overlay AC Roadway and update ADA Ramps | MCK | 2023-04-10 | 8/4/23 | Road Closures, Lane Closures, and Detours & Pedestrian Detours at the intersection of S Livermore Ave. & East/4th | ADA Ramp construction @ insterdection of S Livermore & 4th/East completed Start of pavement rehabilitaion (base repair, overlay, and striping) tentative for LATE JULY Contractor will be providing 72 Hrs notification to affected residents, establishments, and buisnesses
2021 Slurry Seal Project | Citywide In Downtown: (S Livermore/4th/East) | Slurry Seal Roadway and update ADA Ramps | Pavement Coatings Co. | TBD | TBD | Road Closures, Lane Closures, and Detours & Pedestrian Detours at the intersection of S Livermore Ave. & 5th (Tentative mid-late June) | Slurry Seal short section of S H Street between S Livermore Ave and 5th Street - (Tentative mid-late June) Notice to Proceed Pending approval of baseline schedule
Comcast Encroachment Permit | Livermore Village Parking Lot | Install service laterals for downtown establishements (north side) | Comcast / Sefnco | 5/8/23 | TBD | No additional impact - work will be inside L-Street Garage fenced area | No tentative start/resume date at this time
Encroachment Permit No. EN220589 CalWater | 2nd Street between K and L; K Street between 1st and 3rd; J Street between 1st and 3rd | Water main replacement | CalWater | 4/17/23 | 7/17/23 | (Pending approval) Daytime Full Road Closure of 2nd St. from S L St to S J St. Daytime Full Road Closure of S J St and S K Street from 1st St. to 2nd St. (1 day each) Lane Closures on S L Street, 2nd Street, and 3rd Street Loss of parking spaces within closure areas | Installation of new main complete No more night work Restoration work tentative to begin next week during the day time (coordination required) -Grinding and paving of trenches -Slurry Seal 2nd St from S L St. to S J St. -Re-striping of pavement markers
Encroachment Permit No. EN230112 Comcast | S L Street (from 3rd to 5th) | Bore new line and install vaults | Comcast / Sefnco | 4/12/23 | 5/19/23 | Lane closures on S L Street, loss of parking spaces, pedestrian detours | Completed pavement restoration on S L St. Restoration of sidewalk along S L St. ongoing
Encroachment Permit No. EN230004 AT&T | First Street / S J Street | Replace/Splice Fiber Cable | AT&T | TBD | TBD | Loss of Parking Spaces on First Street and S J Street | No Updates this week Permit Issued - Waiting for AT&T to schedule pre-con and provide tentative start date.
Encroachment Permit No. EN230093 AT&T | Railoroad Ave. East of S Livermore Ave. | Traffic Control to access vaults | AT&T | TBD | TBD | Right Lane closure on WB Railroad Ave. | No Updates this week Permit Issued - Waiting for AT&T to schedule pre-con and provide tentative start date.
Encroachment Permit No. EN230095 AT&T | First to Second St. McLeod to Maple | Traffic Control to access pole & vaults | AT&T | TBD | TBD | Work will occupy 4-6 parking spaces at a time between 1st & 2nd /McLeod & Maple | No Updates this week Permit Issued - Waiting for AT&T to schedule pre-con and provide tentative start date.
Encroachment Permit No. EN230101 Mill Springs Apartments | Railoroad Ave. West of S L Street | Planting along frontage of Apartment Complex | A Plus Trees | TBD | TBD | Right Lane closure on EB Railroad Ave. | No Updates this week Start date TBD - Contractor to schedule pre-con with assigned inspector
Encroachment Permit No. EN230172 USPS | S Livermore Ave. In front of Post Office | Remove and Replace Sidewalk | Goebel Construction | 5/25/23 | 5/26/23 | Closure of Sidewalk and Loss of parking spaces in front of post office Pedestrian Detour | Contractor will be working on removing and replacing sidewalk
Encroachment Permit No. EN220452 CalWater | N P Street Locust Street N K Street | Water main replacement | CalWater |  |  | Full street closure on Locust Street | Slurry Seal & place temp striping (S K Street and Locust St - from S K to S L)

## 5-9-23
UPDATED: 5/9/23
PROJECT NAME | LOCATION | DESCRIPTION | AGENCY/ CONTRACTOR/ DEVELOPER | SCHEDULED START | SCHEDULED FINISH | IMPACTS | UPDATES
Trash Enclosure Livermore Village Parking Garage: Phase 1 | Livermore Village Parking Lot | Construct Trash Enclosure and re-pave surface adajcent surface lot in preparation for L-Street Garage construction | WestCal | August 2022 | Late May 2023 | Pedestrian Detours Loss of Parking Spaces | Contractor completed grading work inside the fenced area and is scheduled to pave next week. Water and fire services expected to be complted this week. Will continue working on Trash Enclosure roofing and building exterior Contractor plans to installing light poles this week Contractor expected to clear out from Phase 2 area by May 15 Projected still expected to be substantially complete by LATE MAY 2023
Trash Enclosure Livermore Village Parking Garage: Phase 1 SURFACE IMPROVEMENTS | Livermore Village Parking Lot | Construct Trash Enclosure and re-pave surface adajcent surface lot in preparation for L-Street Garage construction | WestCal | 4/5/23 | Late May 2023 | Loss of 1 or 2 parking spaces and short term closure for striping | Paving and Landscaping work outside the fenced area complete Contractor plans to installing light poles this week Striping of new pavement towards end of May
L-Street Garage Livermore Village Parking Garage: Phase 2 | Livermore Village Veterans Way and S L Street | Construct new L-Street Garage on the corner of S L Street and Veterans Way | Zovich | 4/17/23 | Fall of 2024 | Phased loss of mulitple parking spaces in specific areas of Livermore Village and re-route of parking lot main aisle (K Street) (Up to May 12) Full closure of gravel surface parking area for maximum of 5-days for rehabilitation (May 15-17) Closure of SW corner of Livermore Village (Garage Location) , west half of veterans way including north and south walkways (West of K St), *East sidewalk of S L Street (south of Veterans Way) (Starting May 22) *Closure of EAST sidewalk on S L Street dependent on Installation of L Street Crosswalk & flashing beacon, and opening of S L Street WEST Walkway by Legacy | Contractor continues to work on installation of Vapor Extraction System on the north side parking lot of Livermore Village (gravel area) This work will be followed by the rehabilitation of the gravel parking lot area on MAY 15 Contractor will fence off garage area and west half of Veterans way after the festival - Tentative date 5/22/23 (See impacts) Message boards will be posted 2 weeks in advance to notify public
Livermore Legacy NORTH | First Street / S L Street / Railroad Ave / S M Street | Livermore Legacy Apartments Frontage Improvements | Legacy / SBI | 2021 | LATE July 2023 | Regular RIGHT LANE Closure on EB Railroad Ave. until June Full closure of S M Street for construction of new pavement Lane closure on First Streeet on Friday 5/12/23 for S M Street Paving | Contractor continue to work on First Street imrpovements. The following will occur this week: -Pour Valley gutter 5/9/23 -Pour Blue Stone Sidewalk starting 5/10/23 -Setting trellis posts 5/12/23 First Street Sidewalk and parking areas, and S L Street WEST sidewalk expected to open by the end of May Legacy targeting 6/1/23 for occupancy of Building A (Along First St) S M Street (north of First St) still closed. Paving of Asphalt concrete BASE lift for S M Street scheduled for 5/12/23 Re-opening of Sidewalk on RR Ave pushed back to early June due to an onsite corrective work
2021 Resurfacing Project | Citywide In Downtown: (S Livermore/4th/East) | Overlay AC Roadway and update ADA Ramps | MCK | 2023-04-10 | 8/4/23 | Road Closures, Lane Closures, and Detours & Pedestrian Detours at the intersection of S Livermore Ave. & East/4th | ADA Ramp construction @ insterdection of S Livermore & 4th/East started this week and will be ongoing until mid next week Start of pavement rehabilitaion (base repair, overlay, and striping) tentative for June 15 to August 4 Contractor will be providing 72 Hrs notification to affected residents, establishments, and buisnesses
NEW 2021 Slurry Seal Project | Citywide In Downtown: (S Livermore/4th/East) | Slurry Seal Roadway and update ADA Ramps | Pavement Coatings Co. | TBD | TBD | Road Closures, Lane Closures, and Detours & Pedestrian Detours at the intersection of S Livermore Ave. & 3rd Ave | City to schedule Pre-construction meeting with contractor next week
Comcast Encroachment Permit | Livermore Village Parking Lot | Install service laterals for downtown establishements (north side) | Comcast / Sefnco | 5/8/23 | 5/22/23 | Pedestrian Detours Loss of Parking Spaces | Scheduled to begin this week Pending submittal of City requirements
Encroachment Permit No. EN220589 CalWater | 2nd Street between K and L; K Street between 1st and 3rd; J Street between 1st and 3rd | Water main replacement | CalWater | 4/17/23 | 7/17/23 | NIGHT TIME WORK 9pm-7am Full Road Closures of K Street, J Street between 1st and 2nd Street Lane Closures on S L Street, 2nd Street, and 3rd Street Loss of parking spaces within closure areas | Night time work (9PM-7AM) CWS continous to work on moving service laterals from the old main to the new main. This work will continue up to next week. (installing line stops, installing laterals, Tie-in new main, abandon old main) Locations: J Street (between 1st and 2nd) K Street (between 1st and 3rd) 2nd Street (between S L street and S K Street) Final restoration is scheduled for Late May to Early June
Encroachment Permit No. EN230112 Comcast | S L Street (from 3rd to 5th) | Bore new line and install vaults | Comcast / Sefnco | 4/12/23 | 5/19/23 | Lane closures on S L Street, loss of parking spaces, pedestrian detours | Comcast will continues to bore under the sidewalk on the west side of S L Street from 3rd Street to 5th Street this week Restoration is tentatively scheduled for the week of May 15
Encroachment Permit No. EN230004 AT&T | First Street / S J Street | Replace/Splice Fiber Cable | AT&T | TBD | TBD | Loss of Parking Spaces on First Street and S J Street | No Updates this week Permit Issued - Waiting for AT&T to schedule pre-con and provide tentative start date.
Encroachment Permit No. EN230093 AT&T | Railoroad Ave. East of S Livermore Ave. | Traffic Control to access vaults | AT&T | TBD | TBD | Right Lane closure on WB Railroad Ave. | No Updates this week Permit Issued - Waiting for AT&T to schedule pre-con and provide tentative start date.
Encroachment Permit No. EN230095 AT&T | First to Second St. McLeod to Maple | Traffic Control to access pole & vaults | AT&T | TBD | TBD | Work will occupy 4-6 parking spaces at a time between 1st & 2nd /McLeod & Maple | No Updates this week Permit Issued - Waiting for AT&T to schedule pre-con and provide tentative start date.
Encroachment Permit No. EN230101 Mill Springs Apartments | Railoroad Ave. West of S L Street | Planting along frontage of Apartment Complex | A Plus Trees | TBD | TBD | Right Lane closure on EB Railroad Ave. | No Updates this week Start date TBD - Contractor to schedule pre-con with assigned inspector
Encroachment Permit No. EN230172 USPS | S Livermore Ave. In front of Post Office | Remove and Replace Sidewalk | Goebel Construction | TBD | TBD | Loss of parking spaces in front of post office Pedestrian Detour | Permit issued Start date TBD - Contractor to schedule pre-con
NEW Encroachment Permit No. EN220452 CalWater | N P Street Locust Street N K Street | Water main replacement | CalWater |  |  | Lane closures for restoration work on N P Street / N K Street / Locust Street (May 9 to May 11) | 5/9/23 - Removal of existing pavement markings 5/10/23 - Slurry Seal & place temp striping (S P Street) 5/11/23 - Slurry Seal & place temp striping (S K Street and Locust St)

## 5-3-23
UPDATED: 5/3/23
PROJECT NAME | LOCATION | DESCRIPTION | AGENCY/ CONTRACTOR/ DEVELOPER | SCHEDULED START | SCHEDULED FINISH | IMPACTS | UPDATES
Trash Enclosure Livermore Village Parking Garage: Phase 1 | Livermore Village Parking Lot | Construct Trash Enclosure and re-pave surface adajcent surface lot in preparation for L-Street Garage construction | WestCal | August 2022 | Late MAY 2023 | Pedestrian Detours Loss of Parking Spaces | Will continue working on Trash Enclosure roofing, building exterior, grading and paving inside fenced area, and water/fire services. Will be installing light poles this week Contractor expected to clear out from Phase 2 area by May 10 Projected substantial completion date: Pushed back to LATE MAY 2023
Trash Enclosure Livermore Village Parking Garage: Phase 1 SURFACE IMPROVEMENTS | Livermore Village Parking Lot | Construct Trash Enclosure and re-pave surface adajcent surface lot in preparation for L-Street Garage construction | WestCal | 4/5/23 | Late May 2023 | Loss of 1 or 2 parking spaces and short term closure for striping | Paving and Landscaping work outside the fenced area complete Will be installing light poles this week Striping of new pavement towards end of May
L-Street Garage Livermore Village Parking Garage: Phase 2 | Livermore Village Veterans Way and S L Street | Construct new L-Street Garage on the corner of S L Street and Veterans Way | Zovich | 4/17/23 | Fall of 2024 | Phased loss of mulitple parking spaces in specific areas of Livermore Village and re-route of parking lot main aisle (K Street) Full closure of gravel surface parking area for maximum of 5-days for rehabilitation Closure of SW corner of Livermore Village (Garage Location) , west half of veterans way (West of K St), East sidwalk of S L Street (south of Veterans Way) | Contractor continues to work on installation of Vapor Extraction System on the north side parking lot of Livermore Village (gravel area) This work will be followed by the rehabilitation of the gravel parking lot area in mid-May (see impacts) Contractor will fence off garage area and west half of Veterans way after the festival - Tentative date 5/22/23 (See impacts) Message boards will be posted 2 weeks in advance to notify public Closure of garage area will inlcude closure of east sidewalk of S L Street, contractor will be installing crosswalk to west sidewalk in front of Livermore Legacy
Livermore Legacy NORTH | First Street / S L Street / Railroad Ave / S M Street | Livermore Legacy Apartments Frontage Improvements | Legacy / SBI | 2021 | LATE July 2023 | Long term sidewalk closure on First Street and Occational same day lane closure on S L Street and RR Ave Regular RIGHT LANE Closure on EB Railroad Ave. until June Full closure of S M Street for construction of new pavement | Contractor continue to work on First Street imrpovements. (sidewalk / flex zone area / trellis) First Street Sidewalk and parking areas, and S L Street WEST sidewalk expected to open by the end of May Legacy targeting 6/1/23 for occupancy of Building A (Along First St) S M Street (north of First St) still closed. Contractor completed grading this week. Paving of S M Street tentative for next week. Re-opening of Sidewalk on RR Ave pushed back to early June due to an onsite corrective work
2021 Resurfacing Project | Citywide In Downtown: (S Livermore/4th/East) | Overlay AC Roadway and update ADA Ramps | MCK | 2023-04-10 | 8/4/23 | Road Closures, Lane Closures, and Detours & Pedestrian Detours at the intersection of S Livermore Ave. & East/4th | ADA Ramp construction @ insterdection of S Livermore & 4th/East tentative will be performed on the weekends in conderation of Student pedestrian traffic. Work to begin this weekend 5/6/23 Start of pavement rehabilitaion (base repair, overlay, and striping) tentative for June 15 to August 4 Contractor will be providing 72 Hrs notification to affected residents, establishments, and buisnesses
Comcast Encroachment Permit | Livermore Village Parking Lot | Install service laterals for downtown establishements (north side) | Comcast / Sefnco | 5/8/23 | 5/22/23 | Pedestrian Detours Loss of Parking Spaces | Scheduled to begin next week (week of 5/8/23) pending submittal of City requirements
Encroachment Permit No. EN220589 CalWater | 2nd Street between K and L; K Street between 1st and 3rd; J Street between 1st and 3rd | Water main replacement | CalWater | 4/17/23 | 7/17/23 | NIGHT TIME WORK 9pm-7am Full Road Closures of K Street, J Street between 1st and 2nd Street Lane Closures on S L Street, 2nd Street, and 3rd Street Loss of parking spaces within closure areas | Night time work (9PM-7AM) CWS finished installing all the new mains last week They will manily be working on moving service laterals from the old main to the new main for the next 2 weeks (installing line stops, installing laterals, Tie-in new main, abandon old main) Locations for the next 2 weeks: J Street (between 1st and 3rd) K Street (between 1st and 3rd) 2nd Street (between S L street and S K Street) L Street (between 2nd and 4th) Final restoration is scheduled for Late May to Early June
Encroachment Permit No. EN230112 Comcast | S L Street (from 3rd to 5th) | Bore new line and install vaults | Comcast / Sefnco | 4/12/23 | 5/19/23 | Lane closures on S L Street, loss of parking spaces, pedestrian detours | Comcast will continues to bore under the sidewalk on the west side of S L Street from 3rd Street to 5th Street this week Restoration is tentatively scheduled for the week of May 15
Encroachment Permit No. EN230004 AT&T | First Street / S J Street | Replace/Splice Fiber Cable | AT&T | TBD | TBD | Loss of Parking Spaces on First Street and S J Street | No Updates this week Permit Issued - Waiting for AT&T to schedule pre-con and provide tentative start date.
Encroachment Permit No. EN230093 AT&T | Railoroad Ave. East of S Livermore Ave. | Traffic Control to access vaults | AT&T | TBD | TBD | Right Lane closure on WB Railroad Ave. | No Updates this week Permit Issued - Waiting for AT&T to schedule pre-con and provide tentative start date.
Encroachment Permit No. EN230095 AT&T | First to Second St. McLeod to Maple | Traffic Control to access pole & vaults | AT&T | TBD | TBD | Work will occupy 4-6 parking spaces at a time between 1st & 2nd /McLeod & Maple | No Updates this week Permit Issued - Waiting for AT&T to schedule pre-con and provide tentative start date.
Encroachment Permit No. EN230101 Mill Springs Apartments | Railoroad Ave. West of S L Street | Planting along frontage of Apartment Complex | A Plus Trees | TBD | TBD | Right Lane closure on EB Railroad Ave. | No Updates this week Start date TBD - Contractor to schedule pre-con with assigned inspector
Encroachment Permit No. EN230172 USPS | S Livermore Ave. In front of Post Office | Remove and Replace Sidewalk | Goebel Construction | TBD | TBD | Loss of parking spaces in front of post office Pedestrian Detour | Permit issued Start date TBD - Contractor to schedule pre-con

## 4-26-23
UPDATED: 4/26/23
PROJECT NAME | LOCATION | DESCRIPTION | AGENCY/ CONTRACTOR/ DEVELOPER | SCHEDULED START | SCHEDULED FINISH | IMPACTS | UPDATES
Trash Enclosure Livermore Village Parking Garage: Phase 1 | Livermore Village Parking Lot | Construct Trash Enclosure and re-pave surface adajcent surface lot in preparation for L-Street Garage construction | WestCal | August 2022 | Late MAY 2023 | Pedestrian Detours Loss of Parking Spaces | Contractor completed sewer and landscaping work. Will continue working on Trash Enclosure roofing, building exterior, grading and paving inside fenced area, and water/fire services. Contractor expected to clear out from Phase 2 area by end of April Projected substantial completion date: Pushed back to LATE MAY 2023
Trash Enclosure Livermore Village Parking Garage: Phase 1 SURFACE IMPROVEMENTS | Livermore Village Parking Lot | Construct Trash Enclosure and re-pave surface adajcent surface lot in preparation for L-Street Garage construction | WestCal | 4/5/23 | Late May 2023 | Loss of 1 or 2 parking spaces and short term closure for striping | Paving and Landscaping work outside the fenced area complete Will be installing light poles next Striping of new pavement towards end of May
L-Street Garage Livermore Village Parking Garage: Phase 2 | Livermore Village Veterans Way and S L Street | Construct new L-Street Garage on the corner of S L Street and Veterans Way | Zovich | 4/17/23 | Fall of 2024 | Phased loss of mulitple parking spaces in specific areas of Livermore Village and re-route of parking lot main aisle (K Street) Full closure of gravel surface parking area for maximum of 5-days for rehabilitation | Contractor continues to work on installation of Vapor Extraction System on the north side parking lot of Livermore Village (gravel area) This work will be followed by the rehabilitation of the gravel parking lot area in mid-May (see impacts)
Livermore Legacy NORTH | First Street / S L Street / Railroad Ave / S M Street | Livermore Legacy Apartments Frontage Improvements | Legacy / SBI | 2021 | TBD | Long term sidewalk closure on First Street and Occational same day lane closure on S L Street and RR Ave Regular RIGHT LANE Closure on EB Railroad Ave. until June Full closure of S M Street for construction of new pavement Lane closures/shifts on both directions of S L Street durng work hours | Contractor working on First Street imrpovements. Sidewalk and parking areas expected to open shortly before occupancy of Building along 1st Street Legacy expects to open Building A EARLY JUNE Contractor closed S M Street (north of First St) Currently working on grading for new pavement. Paving of S M Street scheduled for early May Re-opening of Sidewalk on RR Ave pushed back to early June due to an onsite corrective work for backgraded Sanitary Sewer lines. This work requires a daily right lane closure on EB RR Ave. (See impacts) Starting this week Legacy contractor will lower the existing fiber optics line crossing S L Street - See impacts
NEW 2021 Resurfacing Project | Citywide In Downtown: (S Livermore/4th/East) | Overlay AC Roadway and update ADA Ramps | MCK | Mid April | Late September | Lane Closures and Detours & Pedestrian Detours at the intersection of S Livermore Ave. & East/4th | Notice to Proceed - Issued Work @ S Livermore & 4th/East tentative for LATE MAY
Comcast Encroachment Permit | Livermore Village Parking Lot | Install service laterals for downtown establishements (north side) | Comcast / Sefnco | 5/1/23 | 5/22/23 | Pedestrian Detours Loss of Parking Spaces | Permit has been issued Waiting for Comcast to setup Pre-con meeting No updates this week
Encroachment Permit No. EN220589 CalWater | First Street - Alley between Murphy's Paw amd Caratti Jewlers; 2nd Street between K and L; K Street between 1st and 3rd; J Street between 1st and 2nd | Water main replacement | CalWater | 4/17/23 | 7/17/23 | NIGHT TIME WORK 9pm-7pm Full Road Closures of K Street, J Street between 1st and 2nd Street Lane Closures on 2nd and K Street Loss of Parking spaces | CWS currently working NIGHTS installing new water main on J Street and K (between 1st & 2nd Street), and 2nd Street Night time work (9PM-7AM) They will continue to work nights next week to install services in the same vicinity.
Encroachment Permit No. EN230112 Comcast | S L Street (from 3rd to 5th) | Bore new line and install vaults | Comcast / Sefnco | 4/12/23 | 5/1/23 | Lane closures on S L Street, loss of parking spaces, pedestrian detours | Comcast will continues to bore under the sidewalk on the west side of S L Street from 3rd Street to 5th Street this week
Encroachment Permit No. EN230004 AT&T | First Street / S J Street | Replace/Splice Fiber Cable | AT&T | TBD | TBD | Loss of Parking Spaces on First Street and S J Street | No Updates this week Permit Issued - Waiting for AT&T to schedule pre-con and provide tentative start date.
Encroachment Permit No. EN230093 AT&T | Railoroad Ave. East of S Livermore Ave. | Traffic Control to access vaults | AT&T | TBD | TBD | Right Lane closure on WB Railroad Ave. | No Updates this week Permit Issued - Waiting for AT&T to schedule pre-con and provide tentative start date.
Encroachment Permit No. EN230095 AT&T | First to Second St. McLeod to Maple | Traffic Control to access pole & vaults | AT&T | TBD | TBD | Work will occupy 4-6 parking spaces at a time between 1st & 2nd /McLeod & Maple | No Updates this week Permit Issued - Waiting for AT&T to schedule pre-con and provide tentative start date.
Encroachment Permit No. EN230101 Mill Springs Apartments | Railoroad Ave. West of S L Street | Planting along frontage of Apartment Complex | A Plus Trees | TBD | TBD | Right Lane closure on EB Railroad Ave. | No Updates this week Start date TBD - Contractor to schedule pre-con with assigned inspector
NEW Encroachment Permit No. EN230172 USPS | S Livermore Ave. In front of Post Office | Remove and Replace Sidewalk | Goebel Construction | TBD | TBD | Loss of parking spaces in front of post office Pedestrian Detour | Permit issued Start date TBD - Contractor to schedule pre-con

## 4-19-23
UPDATED: 4/19/23
PROJECT NAME | LOCATION | DESCRIPTION | AGENCY/ CONTRACTOR/ DEVELOPER | SCHEDULED START | SCHEDULED FINISH | IMPACTS | UPDATES
Trash Enclosure Livermore Village Parking Garage: Phase 1 | Livermore Village Parking Lot | Construct Trash Enclosure and re-pave surface adajcent surface lot in preparation for L-Street Garage construction | WestCal | August 2022 | Late MAY 2023 | Pedestrian Detours Loss of Parking Spaces | Contractor finished structural steel framing. Will be working on roofing next Will also be working on landscaping & irrigation Continue to work on underground utilities wiithin the Phase 2 (garage) project limits so they can clear out and turn over the area. Projected substantial completion date: Pushed back to LATE MAY 2023
Trash Enclosure Livermore Village Parking Garage: Phase 1 SURFACE IMPROVEMENTS | Livermore Village Parking Lot | Construct Trash Enclosure and re-pave surface adajcent surface lot in preparation for L-Street Garage construction | WestCal | 4/5/23 | Late May 2023 | Loss of 1 or 2 parking spaces and short term closure for striping | Paving work outside the fenced area complete Will be working on landscaping and irrigation Remaining work - Installtion of light poles, and striping - Low impact
L-Street Garage Livermore Village Parking Garage: Phase 2 | Livermore Village Veterans Way and S L Street | Construct new L-Street Garage on the corner of S L Street and Veterans Way | Zovich | Tentative 4/17/23 | Fall of 2024 | Phased loss of mulitple parking spaces in specific areas of Livermore Village and re-route of parking lot main aisle (K Street) | Notice to Proceed issued on 4/17/23 Contractor mobilized construction trailers and currently working on installation of Vapor Extraction System on the north side parking lot of Livermore Village (gravel area)
Livermore Legacy NORTH | First Street / S L Street / Railroad Ave / S M Street | Livermore Legacy Apartments Frontage Improvements | Legacy / SBI | 2021 | TBD | Long term sidewalk closure on First Street and Occational same day lane closure on S L Street and RR Ave Regular RIGHT LANE Closure on EB Railroad Ave. until June Full closure of S M Street for construction of new pavement Lane closures/shifts on both directions of S L Street durng work hours | PGE Power shutdown to completed tie-in work on Railroad Ave. on Sunday 4/16/23 - DAYTIME *Power was off until early Monday (4/17/23) morning - work was delayed due to issues with excavation and shoring Contractor closed S M Street (north of First St) Finished pouring concrete for curb and gutter and driveways. S M Street pavement work (Demo and grading) to begin late this week or early next week TRUCK ENTERING AND LEAVING signs will be posted on 1st Street and S M Street when hauling off demolition debris Re-opening of Sidewalk on RR Ave pushed back to early June due to an onsite corrective work for backgraded Sanitary Sewer lines. This work requires a daily right lane closure on EB RR Ave. (See impacts) Contractor will continue to work on First Street improvements: Grading for sidewalk, curb & gutter, Irrigation sleeves, drilling for trellis posts First Street sidewalk, include the crosswalk crossing S L Street, expected to open shortly before occupancy of Building A (Building along 1st Street) Legacy expects to open Building A EARLY JUNE Starting next week Legacy contractor will lower the existing fiber optics line crossing S L Street - See impacts
NEW 2021 Resurfacing Project | Citywide In Downtown: (S Livermore/4th/East) | Overlay AC Roadway and update ADA Ramps | MCK | Mid April | Late September | Lane Closures and Detours & Pedestrian Detours at the intersection of S Livermore Ave. & East/4th | Notice to Proceed - Issued Work @ S Livermore & 4th/East tentative for LATE MAY
Comcast Encroachment Permit | Livermore Village Parking Lot | Install service laterals for downtown establishements (north side) | Comcast / Sefnco | 4/21/23 | 5/22/23 | Pedestrian Detours Loss of Parking Spaces | Permit has been issued Waiting for Comcast to setup Pre-con meeting
Encroachment Permit No. EN220589 CalWater | First Street - Alley between Murphy's Paw amd Caratti Jewlers; 2nd Street between K and L; K Street between 1st and 3rd; J Street between 1st and 2nd | Water main replacement | CalWater | 4/17/23 | 7/17/23 | Full Road Closures of K Street, J Street between 1st and 2nd Street (Daytime this week - Night Time next week) Lane Closures on 2nd and K Street Loss of Parking spaces | CWS currently working on potholing and saw cutting for their new main on J Street and K (between 1st & 2nd Street) - will require full closure of street during the day (see impacts) For the reamainder of this week they will be working on K Street (between 2nd and 3rd) and 2nd street (between K and L) - See impacts Night time work to begin next week (9PM-7AM)
Encroachment Permit No. EN230112 Comcast | S L Street (from 3rd to 5th) | Bore new line and install vaults | Comcast / Sefnco | 4/12/23 | 4/21/23 | Lane closures on S L Street, loss of parking spaces, pedestrian detours | Comcast will continue to bore under the sidewalk on the west side of S L Street from 3rd Street to 5th Street this week
Encroachment Permit No. EN230004 AT&T | First Street / S J Street | Replace/Splice Fiber Cable | AT&T | TBD | TBD | Loss of Parking Spaces on First Street and S J Street | No Updates this week Permit Issued - Waiting for AT&T to schedule pre-con and provide tentative start date.
Encroachment Permit No. EN230093 AT&T | Railoroad Ave. East of S Livermore Ave. | Traffic Control to access vaults | AT&T | TBD | TBD | Right Lane closure on WB Railroad Ave. | No Updates this week Permit Issued - Waiting for AT&T to schedule pre-con and provide tentative start date.
Encroachment Permit No. EN230095 AT&T | First to Second St. McLeod to Maple | Traffic Control to access pole & vaults | AT&T | TBD | TBD | Work will occupy 4-6 parking spaces at a time between 1st & 2nd /McLeod & Maple | No Updates this week Permit Issued - Waiting for AT&T to schedule pre-con and provide tentative start date.
NEW Encroachment Permit No. EN230101 Mill Springs Apartments | Railoroad Ave. West of S L Street | Planting along frontage of Apartment Complex | A Plus Trees | TBD | TBD | Right Lane closure on EB Railroad Ave. | No Updates this week Start date TBD - Contractor to schedule pre-con with assigned inspector

## 4-11-23
UPDATED: 4/11/23
PROJECT NAME | LOCATION | DESCRIPTION | AGENCY/ CONTRACTOR/ DEVELOPER | SCHEDULED START | SCHEDULED FINISH | IMPACTS | UPDATES
Trash Enclosure Livermore Village Parking Garage: Phase 1 | Livermore Village Parking Lot | Construct Trash Enclosure and re-pave surface adajcent surface lot in preparation for L-Street Garage construction | WestCal | August 2022 | Late MAY 2023 | Pedestrian Detours Loss of Parking Spaces | Contractor continues to work on structural steel and brick facade for the trash enclosure. They will also be working on underground utilities wiithin the Phase 2 (garage) project limits so they can clear out and turn over the area. Projected substantial completion date: Pushed back to LATE MAY 2023 due to weather impacts
Trash Enclosure Livermore Village Parking Garage: Phase 1 SURFACE IMPROVEMENTS | Livermore Village Parking Lot | Construct Trash Enclosure and re-pave surface adajcent surface lot in preparation for L-Street Garage construction | WestCal | 4/5/23 | Early May 2023 | Loss of 1 or 2 parking spaces and short term closure for striping | Paving work outside the fenced area was completed last week Remaining work - Landscaping, installtion of light poles, and striping - Low impact
L-Street Garage Livermore Village Parking Garage: Phase 2 | Livermore Village Veterans Way and S L Street | Construct new L-Street Garage on the corner of S L Street and Veterans Way | Zovich | Tentative 4/17/23 | Fall of 2024 | Phased loss of mulitple parking spaces in specific areas of Livermore Village and re-route of parking lot main aisle (K Street) | Tentative Notice to Proceed issue date 4/17/23 For the first 4 weeks, the contractor will be working on installation of Vapor Extraction System on the north side parking lot of Livermore Village (gravel area)
Livermore Legacy NORTH | First Street / S L Street / Railroad Ave / S M Street | Livermore Legacy Apartments Frontage Improvements | Legacy / SBI | 2021 | TBD | Long term sidewalk closure on First Street and Occational same day lane closure on S L Street and RR Ave Regular RIGHT LANE Closure on EB Railroad Ave. for 2 months (Started this week) Full closure of S M Street for construction of new pavement | PGE Power shutdown to perform tie-in work on Railroad Ave. Scheduled for Sunday 4/16/23 - DAYTIME Re-opening of Sidewalk on RR Ave pushed back due to PGE delay Contractor working on First Street improvements: Grading for sidewalk, curb & gutter, Irrigation sleeves, drilling for trellis posts First Street sidewalk, include the crosswalk crossing S L Street, expected to open shortly before occupancy of Building A (Building along 1st Street) Legacy expects to open Building A EARLY JUNE Contractor closed S M Street (north of First St) And currently working on construction of the curb and gutter and driveways Pavement work (Demo and grading) tentative consecutive dry weather days Contractor working on ONSITE sewer issues that requires lane closure on EB RR Ave (See impacts)
NEW 2021 Resurfacing Project | Citywide In Downtown: (S Livermore/4th/East) | Overlay AC Roadway and update ADA Ramps | MCK | Mid April | Late September | Lane Closures and Detours & Pedestrian Detours at the intersection of S Livermore Ave. & East/4th | Notice to Proceed - Issued Work @ S Livermore & 4th/East tentative for LATE MAY
Comcast Encroachment Permit | Livermore Village Parking Lot | Install service laterals for downtown establishements (north side) | Comcast / Sefnco | 4/21/23 | 5/22/23 | Pedestrian Detours Loss of Parking Spaces | Permit has been issued installation of laterals along west side to start 4/21/23
Encroachment Permit No. EN220589 CalWater | First Street - Alley between Murphy's Paw amd Caratti Jewlers; 2nd Street between K and L; K Street between 1st and 3rd; J Street between 1st and 2nd | Water main replacement | CalWater | 4/17/23 | 7/17/23 | Full Road Closures of K Street, J Street between 1st and 2nd Street (2 days of daytime closure on K and 2 days of daytime closure on J Street after) Daytime Lane Closures on 2nd and 3rd Street Loss of Parking spaces | Permit Issued Tentative Start Date 4/17/23 CWS will pothole and sawcut on J Street and K Street next week - will require full closure of street (see impacts) CWS to issue notification letter this week NO PARKING signs tobe posted no later than Friday
Encroachment Permit No. EN230112 Comcast | S L Street (from 3rd to 5th) | Bore new line and install vaults | Comcast / Sefnco | 4/12/23 | 4/21/23 | Lane closures on S L Street, loss of parking spaces, pedestrian detours | Starting 4/12/23 Comcast will be boring under the sidewalk on the west side of S L Street from 3rd Street to 5th Street
Encroachment Permit No. EN230004 AT&T | First Street / S J Street | Replace/Splice Fiber Cable | AT&T | TBD | TBD | Loss of Parking Spaces on First Street and S J Street | No Updates this week Permit Issued - Waiting for AT&T to schedule pre-con and provide tentative start date.
Encroachment Permit No. EN230093 AT&T | Railoroad Ave. East of S Livermore Ave. | Traffic Control to access vaults | AT&T | TBD | TBD | Right Lane closure on WB Railroad Ave. | No Updates this week Permit Issued - Waiting for AT&T to schedule pre-con and provide tentative start date.
Encroachment Permit No. EN230095 AT&T | First to Second St. McLeod to Maple | Traffic Control to access pole & vaults | AT&T | TBD | TBD | Work will occupy 4-6 parking spaces at a time between 1st & 2nd /McLeod & Maple | No Updates this week Permit Issued - Waiting for AT&T to schedule pre-con and provide tentative start date.
NEW Encroachment Permit No. EN230101 Mill Springs Apartments | Railoroad Ave. West of S L Street | Planting along frontage of Apartment Complex | A Plus Trees | TBD | TBD | Right Lane closure on EB Railroad Ave. | No Updates this week Start date TBD - Contractor to schedule pre-con with assigned inspector

## 3-28-23
UPDATED: 3/28/23
PROJECT NAME | LOCATION | DESCRIPTION | AGENCY/ CONTRACTOR/ DEVELOPER | SCHEDULED START | SCHEDULED FINISH | IMPACTS | UPDATES
Trash Enclosure Livermore Village Parking Garage: Phase 1 | Livermore Village Parking Lot | Construct Trash Enclosure and re-pave surface adajcent surface lot in preparation for L-Street Garage construction | WestCal | August 2022 | Early MAY 2023 | Pedestrian Detours Loss of Parking Spaces | Contractor will be working on structural steel and roofing for the trash enclosure and continue to work on the remaining concrete improvements inside fenced area this week Projected substantial completion date: Pushed back to EARLY MAY 2023 due to weather impacts
Trash Enclosure Livermore Village Parking Garage: Phase 1 SURFACE IMPROVEMENTS | Livermore Village Parking Lot | Construct Trash Enclosure and re-pave surface adajcent surface lot in preparation for L-Street Garage construction | WestCal | 4/5/23 | 4/11/23 | Designated access route will be closed No delivery access to backside of businesses Revised garbage pickup location Pedestrian Detours Loss of Parking Spaces | Work outside the fenced area currently suspended due to weather Contractor currently waiting for a window of 5-consecutive days to complete the remainder of the work outside the fence. Tentative date to resume: First week of April Remaining work includes demolition of the existing pavement, grading, and repaving of the surface lot
L-Street Garage Livermore Village Parking Garage: Phase 2 | Livermore Village Veterans Way and S L Street | Construct new L-Street Garage on the corner of S L Street and Veterans Way | Zovich | Tentative 4/3/23 | Summer of 2024 | Pedestrian Detours Loss of Parking Spaces Long Term Road Closures | Tentative Notice to Proceed issue date 4/3/23 This date is pending Schedule Approval - City sent back review comments last Friday 3/24/23 First week - Contractor will work on gravel lot improvements (NE corner of Lot) & Mobilization
Livermore Legacy NORTH | First Street / S L Street / Railroad Ave / S M Street | Livermore Legacy Apartments Frontage Improvements | Legacy / SBI | 2021 | TBD | Long term sidewalk closure on First Street and Occational same day lane closure on S L Street and RR Ave Regular RIGHT LANE Closure on EB Railroad Ave. for 2 months (Started this week) Full closure of S M Street for construction of new pavement - Tentative EARLY-April Lane closures/shifts on both directions of S L Street during work hours on early April | PGE CANCELLED Power shutdown to perform tie-in work on Railroad Ave. that was scheduled for last Sunday 3/26/23 THIS WORK HAS BEEN RESCHEDULED FOR 4/16/23 (Daytime) Re-opening of Sidewalk on RR Ave pushed back due to PGE delay Contractor working on ONSITE sewer issues that requires lane closure on EB RR Ave (See impacts) All grading work on First Street postponed due to weather - SBI waiting for grade to dry out to resume work First Street sidewalk, include the crosswalk crossing S L Street, expected to open shortly before occupancy of Building A (Building along 1st Street) Legacy expects to open Building A EARLY JUNE Installation of Street lights along all sides of the development to begin first week of April Contractor plans to CLOSE S M Street NEXT WEEK pending City Approval Contractor will work on curb and gutter along the west and north side of the street. Pavement work (Demo and grading) tentative consecutive dry weather days Lowering of the existing fiber optics line crossing S L Street postponed to occur concurrent with S M Street Closure
NEW 2021 Resurfacing Project | Citywide In Downtown: (S Livermore/4th/East) | Overlay AC Roadway and update ADA Ramps | MCK | Mid April | Late September | Lane Closures and Detours & Pedestrian Detours at the intersection of S Livermore Ave. & East/4th | Notice to Proceed - Tentative for MID APRIL Work @ S Livermore & 4th/East tentative for LATE MAY
Comcast Encroachment Permit | Livermore Village Parking Lot | Install service laterals for downtown establishements (north side) | Comcast / Sefnco | TBD | TBD | Pedestrian Detours Loss of Parking Spaces | No Updates this week *Comcast has applied for the permit to install laterals to each building - Currently under City Review
Encroachment Permit No. EN220589 CalWater | First Street - Alley between Murphy's Paw amd Caratti Jewlers; 2nd Street between K and L; K Street between 1st and 3rd; J Street between 1st and 2nd | Water main replacement | CalWater | TBD | TBD | Road Closures on First Street, K Street, J Street (Night Work) in downtown core Daytime Lane Closures on 2nd and 3rd Street | No Updates this week Permit for work in various locations in downtown core soon to be issued. CWS to setup Pre-construction meeting with City. Start date pending City approval or work plan and sequence of work.
Encroachment Permit No. EN230004 AT&T | First Street / S J Street | Replace/Splice Fiber Cable | AT&T | TBD | TBD | Loss of Parking Spaces on First Street and S J Street | No Updates this week Permit Issued - Waiting for AT&T to schedule pre-con and provide tentative start date.
Encroachment Permit No. EN230093 AT&T | Railoroad Ave. East of S Livermore Ave. | Traffic Control to access vaults | AT&T | TBD | TBD | Right Lane closure on WB Railroad Ave. | No Updates this week Permit Issued - Waiting for AT&T to schedule pre-con and provide tentative start date.
Encroachment Permit No. EN230095 AT&T | First to Second St. McLeod to Maple | Traffic Control to access pole & vaults | AT&T | TBD | TBD | Work will occupy 4-6 parking spaces at a time between 1st & 2nd /McLeod & Maple | No Updates this week Permit Issued - Waiting for AT&T to schedule pre-con and provide tentative start date.
NEW Encroachment Permit No. EN230101 Mill Springs Apartments | Railoroad Ave. West of S L Street | Planting along frontage of Apartment Complex | A Plus Trees | TBD | TBD | Right Lane closure on EB Railroad Ave. | No Updates this week Start date TBD - Contractor to schedule pre-con with assigned inspector

## 3-14-23
UPDATED: 3/14/23
PROJECT NAME | LOCATION | DESCRIPTION | AGENCY/ CONTRACTOR/ DEVELOPER | SCHEDULED START | SCHEDULED FINISH | IMPACTS | UPDATES
Trash Enclosure Livermore Village Parking Garage: Phase 1 | Livermore Village Parking Lot | Construct Trash Enclosure and re-pave surface adajcent surface lot in preparation for L-Street Garage construction | WestCal | August 2022 | Early April 2023 | Pedestrian Detours Loss of Parking Spaces | Contractor still working on CMU Walls - Currently on their 7th week. Completion date continues to be pushed back due to weather. Also currently working on drainage and sewer Projected substantial completion date: Pushed back to early April 2023 due to weather impacts
Trash Enclosure Livermore Village Parking Garage: Phase 1 SURFACE IMPROVEMENTS | Livermore Village Parking Lot | Construct Trash Enclosure and re-pave surface adajcent surface lot in preparation for L-Street Garage construction | WestCal | 3/1/23 | TBD | Designated access route will be closed No delivery access to backside of businesses Revised garbage pickup location Pedestrian Detours Loss of Parking Spaces | Work outside the fenced area currently suspended due to weather Fences have been moved back and access route re-opened. *Contractor was able to complete most of the surface lot concrete imrpovements outside the fenced area before suspending work. Contractor currently waiting for a window of 5-consecutive days to complete the remainder of the work outside the fence. Remaining work includes demolition of the existing pavement, grading, and repaving of the surface lot
L-Street Garage Livermore Village Parking Garage: Phase 2 | Livermore Village Veterans Way and S L Street | Construct new L-Street Garage on the corner of S L Street and Veterans Way | Zovich | Tentative 3/13/23 | Summer of 2024 | Pedestrian Detours Loss of Parking Spaces Long Term Road Closures | Notice to Proceed issue date pushed back to 4/3/23 as a result of the Project Schedule review. *This date is pending approval of resubmitted schedule *Contractor is still working on resubmitting their baseline schedule. *Submitted schedule missing important dates that will impact downtown coordination
Livermore Legacy NORTH | First Street / S L Street / Railroad Ave / S M Street | Livermore Legacy Apartments Frontage Improvements | Legacy / SBI | 2021 | TBD | Long term sidewalk closure on First Street and Occational same day lane closure on S L Street and RR Ave 8 hour(+/-) Power shutdown for residents and some businesses when PGE does Legacy electrical tie-in on RR Ave. Full closure of S M Street for construction of new pavement - Tentative mid-April Lane closures/shifts on both directions of S L Street durng work hours | PGE Power shutdown to perform tie-in work on Railroad Ave. Scheduled for Sunday 3/26/23 - DAYTIME Re-opening of Sidewalk on RR Ave pushed back to early April due to PGE delay All grading work on First Street postponed due to weather First Street sidewalk expected to be open to public by early May, this will include the crosswalk crossing S L Street Contractor will begin working on the S M Street Pavement this April. This work was pushed back due to weather and will require a full closure of the road (see impacts) Starting mid-next week Legacy contractor will lower the existing fiber optics line crossing S L Street - See impacts Legacy Contractor and City staff continue to enforce NO CONSTRUCTION PARKING on the SW corner of Livermore village. Contractor has put up "NO LEGACY CONSTRUCTION PARKING" at the driveway entrance to this area
Livermore Legacy SOUTH | First Street - From S L Street to S M Street (South side) | First Street streetscape improvements | Legacy / Goodfellow Bros | 2019 | Substantially Complete | N/A | Project is substantially complete NO MORE ANTICIPATED FIELD WORK
Comcast Encroachment Permit | Livermore Village Parking Lot | Install service laterals for downtown establishements (north side) | Comcast / Sefnco | TBD | TBD | Pedestrian Detours Loss of Parking Spaces | *Comcast has applied for the permit to install laterals to each building - Currently under City Review
Encroachment Permit No. EN220589 CalWater | First Street - Alley between Murphy's Paw amd Caratti Jewlers; 2nd Street between K and L; K Street between 1st and 3rd; J Street between 1st and 2nd | Water main replacement | CalWater | TBD | TBD | Road Closures on First Street, K Street, J Street (Night Work) in downtown core Daytime Lane Closures on 2nd and 3rd Street | Permit for work in various locations in downtown core soon to be issued. CWS to setup Pre-construction meeting with City. Start date pending City approval or work plan and sequence of work.
Encroachment Permit No. EN230004 AT&T | First Street / S J Street | Replace/Splice Fiber Cable | AT&T | TBD | TBD | Loss of Parking Spaces on First Street and S J Street | Permit Issued - Waiting for AT&T to schedule pre-con and provide tentative start date.
Encroachment Permit No. EN230093 AT&T | Railoroad Ave. East of S Livermore Ave. | Traffic Control to access vaults | AT&T | TBD | TBD | Right Lane closure on WB Railroad Ave. | Permit Issued - Waiting for AT&T to schedule pre-con and provide tentative start date.
Encroachment Permit No. EN230095 AT&T | First to Second St. McLeod to Maple | Traffic Control to access pole & vaults | AT&T | TBD | TBD | Work will occupy 4-6 parking spaces at a time between 1st & 2nd /McLeod & Maple | Permit Issued - Waiting for AT&T to schedule pre-con and provide tentative start date.

## 3-21-23
UPDATED: 3/21/23
PROJECT NAME | LOCATION | DESCRIPTION | AGENCY/ CONTRACTOR/ DEVELOPER | SCHEDULED START | SCHEDULED FINISH | IMPACTS | UPDATES
Trash Enclosure Livermore Village Parking Garage: Phase 1 | Livermore Village Parking Lot | Construct Trash Enclosure and re-pave surface adajcent surface lot in preparation for L-Street Garage construction | WestCal | August 2022 | LATE April 2023 | Pedestrian Detours Loss of Parking Spaces | Contractor will be working on concrete improvements and underground utilities inside fenced area this week CMU wall work completed Projected substantial completion date: Pushed back to LATE April 2023 due to weather impacts
Trash Enclosure Livermore Village Parking Garage: Phase 1 SURFACE IMPROVEMENTS | Livermore Village Parking Lot | Construct Trash Enclosure and re-pave surface adajcent surface lot in preparation for L-Street Garage construction | WestCal | 3/1/23 | TBD | Designated access route will be closed No delivery access to backside of businesses Revised garbage pickup location Pedestrian Detours Loss of Parking Spaces | Work outside the fenced area currently suspended due to weather Contractor currently waiting for a window of 5-consecutive days to complete the remainder of the work outside the fence. Tentative date to resume: First week of April Remaining work includes demolition of the existing pavement, grading, and repaving of the surface lot
L-Street Garage Livermore Village Parking Garage: Phase 2 | Livermore Village Veterans Way and S L Street | Construct new L-Street Garage on the corner of S L Street and Veterans Way | Zovich | Tentative 3/13/23 | Summer of 2024 | Pedestrian Detours Loss of Parking Spaces Long Term Road Closures | Notice to Proceed issue date 4/3/23 as a result of the Project Schedule review. *This date is pending approval of resubmitted schedule *City and Consultants currently reviewing resubmitted baseline schedule
Livermore Legacy NORTH | First Street / S L Street / Railroad Ave / S M Street | Livermore Legacy Apartments Frontage Improvements | Legacy / SBI | 2021 | TBD | Long term sidewalk closure on First Street and Occational same day lane closure on S L Street and RR Ave 8 hour(+/-) Power shutdown for residents and some businesses when PGE does Legacy electrical tie-in on RR Ave. Full closure of S M Street for construction of new pavement - Tentative mid-April Lane closures/shifts on both directions of S L Street durng work hours | PGE Power shutdown to perform tie-in work on Railroad Ave. Scheduled for Sunday 3/26/23 - DAYTIME Pre-con scheduled for 3/23/23 Re-opening of Sidewalk on RR Ave pushed back to early April due to PGE delay All grading work on First Street postponed due to weather - SBI waiting for grade to dry out to resume work First Street sidewalk expected to be open to public by early May, this will include the crosswalk crossing S L Street Installation of Street lights along all sides of the development to begin first week of April Contractor will begin working on the S M Street Pavement MID April. This work was pushed back due to weather and will require a full closure of the road (see impacts) Lowering of the existing fiber optics line crossing S L Street postponed to next week due to weather - See impacts
Livermore Legacy SOUTH | First Street - From S L Street to S M Street (South side) | First Street streetscape improvements | Legacy / Goodfellow Bros | 2019 | Substantially Complete | N/A | Project is substantially complete NO MORE ANTICIPATED FIELD WORK
NEW 2021 Resurfacing Project | Citywide In Downtown: (S Livermore/4th/East) | Overlay AC Roadway and update ADA Ramps | MCK | Later March | Mid September | Lane Closures and Detours & Pedestrian Detours at the intersection of S Livermore Ave. & East/4th | Notice to Proceed - Tentative for LATE MARCH Work @ S Livermore & 4th/East tentative for FIRST WEEK OF MAY
Comcast Encroachment Permit | Livermore Village Parking Lot | Install service laterals for downtown establishements (north side) | Comcast / Sefnco | TBD | TBD | Pedestrian Detours Loss of Parking Spaces | *Comcast has applied for the permit to install laterals to each building - Currently under City Review
Encroachment Permit No. EN220589 CalWater | First Street - Alley between Murphy's Paw amd Caratti Jewlers; 2nd Street between K and L; K Street between 1st and 3rd; J Street between 1st and 2nd | Water main replacement | CalWater | TBD | TBD | Road Closures on First Street, K Street, J Street (Night Work) in downtown core Daytime Lane Closures on 2nd and 3rd Street | Permit for work in various locations in downtown core soon to be issued. CWS to setup Pre-construction meeting with City. Start date pending City approval or work plan and sequence of work.
Encroachment Permit No. EN230004 AT&T | First Street / S J Street | Replace/Splice Fiber Cable | AT&T | TBD | TBD | Loss of Parking Spaces on First Street and S J Street | Permit Issued - Waiting for AT&T to schedule pre-con and provide tentative start date.
Encroachment Permit No. EN230093 AT&T | Railoroad Ave. East of S Livermore Ave. | Traffic Control to access vaults | AT&T | TBD | TBD | Right Lane closure on WB Railroad Ave. | Permit Issued - Waiting for AT&T to schedule pre-con and provide tentative start date.
Encroachment Permit No. EN230095 AT&T | First to Second St. McLeod to Maple | Traffic Control to access pole & vaults | AT&T | TBD | TBD | Work will occupy 4-6 parking spaces at a time between 1st & 2nd /McLeod & Maple | Permit Issued - Waiting for AT&T to schedule pre-con and provide tentative start date.
NEW Encroachment Permit No. EN230101 Mill Springs Apartments | Railoroad Ave. West of S L Street | Planting along frontage of Apartment Complex | A Plus Trees | TBD | TBD | Right Lane closure on EB Railroad Ave. | Start date TBD - Contractor to schedule pre-con with assigned inspector

## 3-7-23
UPDATED: 3/7/23
PROJECT NAME | LOCATION | DESCRIPTION | AGENCY/ CONTRACTOR/ DEVELOPER | SCHEDULED START | SCHEDULED FINISH | IMPACTS | UPDATES
Trash Enclosure Livermore Village Parking Garage: Phase 1 | Livermore Village Parking Lot | Construct Trash Enclosure and re-pave surface adajcent surface lot in preparation for L-Street Garage construction | WestCal | August 2022 | Early April 2023 | Pedestrian Detours Loss of Parking Spaces | Contractor still working on CMU Walls - Currently on their 6th week. Completion date continues to be pushed back due to weather. Projected substantial completion date: Pushed back to early April 2023 due to weather impacts
Trash Enclosure Livermore Village Parking Garage: Phase 1 SURFACE IMPROVEMENTS | Livermore Village Parking Lot | Construct Trash Enclosure and re-pave surface adajcent surface lot in preparation for L-Street Garage construction | WestCal | 3/1/23 | TBD | Designated access route will be closed No delivery access to backside of businesses Revised garbage pickup location Pedestrian Detours Loss of Parking Spaces | Work outside the fenced area started last week but will be suspended due to weather Contractor will be moving back fences tomorrow 3/8/23 to re-open the access route. Contractor requires a window of 5-consecutive days to complete the remainder of the offsite work. This work includes demolition of the existing pavement, grading, and repaving of the surface lot
L-Street Garage Livermore Village Parking Garage: Phase 2 | Livermore Village Veterans Way and S L Street | Construct new L-Street Garage on the corner of S L Street and Veterans Way | Zovich | Tentative 3/13/23 | Summer of 2024 | Pedestrian Detours Loss of Parking Spaces Long Term Road Closures | Notice to Proceed issue date pushed back to 3/13/26 as a result of the Project Schedule review. *This date is pending approval of resubmitted schedule Submitted schedule missing important dates that will impact downtown coordination
Livermore Legacy NORTH | First Street / S L Street / Railroad Ave / S M Street | Livermore Legacy Apartments Frontage Improvements | Legacy / SBI | 2021 | TBD | Long term sidewalk closure on First Street and Occational same day lane closure on S L Street and RR Ave Pedestrian detour and Closure of NB S M Street between 2nd and 1st during business hours ONLY for PGE Gas Tie-in (3/3/23 - 3/8/23) - weekends not included - will be re-opended after work hours Full closure of S M Street for construction of new pavement - start date pending weather | PGE cancelled their 2/25/23 tie-in work on RR Ave. due to resources being diverted to assist with the PGE storm restoration efforts Tentatively rescheduled for Sunday 3/26/23 - DAYTIME Re-opening of Sidewalk on RR Ave pushed back to early April due to PGE delay Ramp at the SW corner of RR Ave. and S L Street has been re-opened. Pedestrians are able to use all the crosswalks in that intersection. PGE gas tie in on First street started last week and will be completed tomorrow Wednesday 3/8/23 - See impacts All grading work on First Street postponed due to weather First Street sidewalk expected to be open to public by early April, this will include the crosswalk crossing S L Street Contractor will begin working on the S M Street Pavement this March. This work will require a full closure of the road (see impacts) Legacy Contractor and City staff continue to enforce NO CONSTRUCTION PARKING on the SW corner of Livermore village. Contractor has put up "NO LEGACY CONSTRUCTION PARKING" at the driveway entrance to this area
Livermore Legacy SOUTH | First Street - From S L Street to S M Street (South side) | First Street streetscape improvements | Legacy / Goodfellow Bros | 2019 | Substantially Complete | N/A | Project is substantially complete NO MORE ANTICIPATED FIELD WORK
Encroachment Permit No. EN220465 Comcast | Livermore Village Parking Lot | Install new service line behind downtown establishements (north side) | Comcast / Sefnco | January 20, 2023 | Permit work COMPLETE End of March (For all other Comcast Work in this area noted but not covered under this permit) | Pedestrian Detours Loss of Parking Spaces In Private Property (Madden) | Permit work Icompleted. *Comcast scheduled to install private portion of the run (Madden Property parking area) this week *Comcast has applied for the permit to install laterals to each building - start date TBD
CalWater Water Line Replacement | First Street - Alley between Murphy's Paw amd Caratti Jewlers; 2nd Street between K and L; K Street between 1st and 3rd; J Street between 1st and 2nd | Water main replacement | CalWater | TBD | TBD | Lane Closures Pedestrian Detours Loss of Parking Spaces in Downtown Core Area | CWS eliminated the main replacement in the downtown alley way from the scope of this permit. Permit work for other locations in downtown core has not been issued. CWS continues to work with City regardin impacts and Traffic Control.
Underground Tank Removal | Parking Lot north of La Botica | Remove Underground Tank that was discovered first week of January | Pangea | 2nd week of February | 4th week of February | N/A | WORK COMPLETE Tank pit backfilled and parking area re-opened to public on Friday 3/3/23
Encroachment Permit No. EN230004 AT&T | First Street / S J Street | Replace/Splice Fiber Cable | AT&T | TBD | TBD | Loss of Parking Spaces on First Street and S J Street | Permit Issued - Waiting for AT&T to schedule pre-con and provide tentative start date.
Encroachment Permit No. EN230093 AT&T | Railoroad Ave. East of S Livermore Ave. | Traffic Control to access vaults | AT&T | TBD | TBD | Right Lane closure on WB Railroad Ave.
Encroachment Permit No. EN230095 AT&T | First to Second St. McLeod to Maple | Traffic Control to access pole & vaults | AT&T | TBD | TBD | Work will occupy 4-6 parking spaces at a time between 1st & 2nd /McLeod & Maple
Encroachment Permit No. EN220287 AT&T | Second to Third St. K St to L St | Traffic Control to access vaults | AT&T | 2/27/23 | 3/3/23 | Work will occupy 2-4 parking spaces at a time between 2nd & 3rd /S K St & S J St | WORK COMPLETE

## 2-28-23
UPDATED: 2/28/23
PROJECT NAME | LOCATION | DESCRIPTION | AGENCY/ CONTRACTOR/ DEVELOPER | SCHEDULED START | SCHEDULED FINISH | IMPACTS | UPDATES
Trash Enclosure Livermore Village Parking Garage: Phase 1 | Livermore Village Parking Lot | Construct Trash Enclosure and re-pave surface adajcent surface lot in preparation for L-Street Garage construction | WestCal | August 2022 | Late March 2023 | Pedestrian Detours Loss of Parking Spaces | Contractor still working on CMU Walls - Currently on their 5th week. Completion date pushed back to next week due to weather. Completion next week is also weather dependent Contractor will be pouring back the concrete for the sidewalk & ramp corrective work on east of the fenced area. Sidewalk and Ramp to be re-opened to public Monday 3/6/23 Projected substantial completion date: Still projected for Late-March 2023
Trash Enclosure Livermore Village Parking Garage: Phase 1 SURFACE IMPROVEMENTS | Livermore Village Parking Lot | Construct Trash Enclosure and re-pave surface adajcent surface lot in preparation for L-Street Garage construction | WestCal | 3/1/23 | 3/14/23 | Designated access route will be closed No delivery access to backside of businesses Revised garbage pickup location Pedestrian Detours Loss of Parking Spaces | Work outside the fenced area will begin tomorrow 3/1/23 Businesses were notified last week and are aware of modifications to garabage pickup locations. Contractor coordinated with Livermore Sanitation revised pickup locations This work includes repaving surface lot and installation of new street lights and planter areas Contract allows a total of 10-days for this work
L-Street Garage Livermore Village Parking Garage: Phase 2 | Livermore Village Veterans Way and S L Street | Construct new L-Street Garage on the corner of S L Street and Veterans Way | Zovich | Tentative 3/6/23 | Summer of 2024 | Pedestrian Detours Loss of Parking Spaces Long Term Road Closures | Notice to Proceed scheduled issue date 3/6/26 Construction schedule submitted for Review
Livermore Legacy NORTH | First Street / S L Street / Railroad Ave / S M Street | Livermore Legacy Apartments Frontage Improvements | Legacy / SBI | 2021 | TBD | Long term sidewalk closure on First Street and Occational same day lane closure on S L Street and RR Ave Pedestrian detour and Closure of NB S M Street between 2nd and 1st during business hours ONLY for PGE Gas Tie-in (3/3/23 - 3/8/23) - weekends not included - will be re-opended after work hours Full closure of S M Street for construction of new pavement starting 2nd week of March- (2-3 weeks) | PGE cancelled their 2/25/23 tie-in work on RR Ave. due to resources being diverted to assist with the PGE storm restoration efforts Tentatively rescheduled for Sunday 3/26/23 - DAYTIME Re-opening of Sidewalk on RR Ave pushed back to early April due to PGE delay Ramp at the SW corner of RR Ave. and S L Street has been re-opened. Pedestrians are able to use all the crosswalks in that intersection. PGE gas tie in on First street work will begin this week starting Friday 3/3/23 - See impacts All grading work on First Street postponed due to weather First Street sidewalk expected to be open to public by early April, this will include the crosswalk crossing S L Street Pouring of section of curb and gutter on the EAST side of S M Street is scheduled for end of this week Contractor will begin working on the S M Street Pavement on the 2nd week of March. This work will require a full closure of the road (see impacts) Legacy Contractor will be putting up this week NO LEGACY CONSTRUCTION PARKING signs for the parking area on the SW corner of Livermore village
Livermore Legacy SOUTH | First Street - From S L Street to S M Street (South side) | First Street streetscape improvements | Legacy / Goodfellow Bros | 2019 | End of Feb 2023 | Loss of single parking spaces - Only as needed | Project is substantially complete and contractor just working on minor punchlist items.
Encroachment Permit No. EN220465 Comcast | Livermore Village Parking Lot | Install new service line behind downtown establishements (north side) | Comcast / Sefnco | January 20, 2023 | End of March (For all other Comcast Work noted that is not assoociated with this permit) | Pedestrian Detours Loss of Parking Spaces | Installation work completed. *Comcast scheduled to install private portion of the run (Madden Property parking area) on 3/7/23 - Not part of this permit *Comcast has applied for the permit to install laterals to each building - start date TBD
CalWater Water Line Replacement | First Street - Alley between Murphy's Paw amd Caratti Jewlers; 2nd Street between K and L; K Street between 1st and 3rd; J Street between 1st and 2nd | Water main replacement | CalWater | Mid March 2023 | Early April | Lane Closures Pedestrian Detours Loss of Parking Spaces in Downtown Core Area | CWS eliminated the main replacement in the downtown alley way from the scope of this permit. Permit work for other locations in downtown core has not been issued. CWS continues to work with City regardin impacts and Traffic Control.
Underground Tank Removal | Parking Lot north of La Botica | Remove Underground Tank that was discovered first week of January | Pangea | 2nd week of February | 4th week of February | Pedestrian Detours and Loss of About 20 parking spaces for this entire week behind Plucked Chicken and Caratti Jewlers | Received Approval from LPFD/County/Water Quality Board on 2/24/23 to backfill pit. Backfilling scheduled for Thursday 3/2/23. Parking spaces to be re-opened to public that same day.
Encroachment Permit No. EN230004 AT&T | First Street / S J Street | Replace/Splice Fiber Cable | AT&T | TBD | TBD | Loss of Parking Spaces on First Street and S J Street | Permit Issued - Waiting for AT&T to schedule pre-con and provide tentative start date.
Encroachment Permit No. EN230093 AT&T | Railoroad Ave. East of S Livermore Ave. | Traffic Control to access vaults | AT&T | TBD | TBD | Right Lane closure on WB Railroad Ave.
Encroachment Permit No. EN230095 AT&T | First to Second St. McLeod to Maple | Traffic Control to access pole & vaults | AT&T | TBD | TBD | Work will occupy 4-6 parking spaces at a time between 1st & 2nd /McLeod & Maple
Encroachment Permit No. EN220287 AT&T | Second to Third St. K St to L St | Traffic Control to access vaults | AT&T | 2/27/23 | 3/3/23 | Work will occupy 2-4 parking spaces at a time between 2nd & 3rd /S K St & S J St | Work ongoing at various locations (see impacts)

## 2-22-23
UPDATED: 2/22/23
PROJECT NAME | LOCATION | DESCRIPTION | AGENCY/ CONTRACTOR/ DEVELOPER | SCHEDULED START | SCHEDULED FINISH | IMPACTS | UPDATES
Trash Enclosure Livermore Village Parking Garage: Phase 1 | Livermore Village Parking Lot | Construct Trash Enclosure and re-pave surface adajcent surface lot in preparation for L-Street Garage construction | WestCal | August 2022 | Late March 2023 | Pedestrian Detours Loss of Parking Spaces | Contractor still working on CMU Walls - they are currently on their 4th week. Work is falling behind and is now expected to take 5 weeks total. Completion next week is weather dependent Contractor also working on corrective work on sidewalk & ramp on east of the fenced area. They expect to complete this work early next week. They will resume Sanitary Sewer work inside the fenced area next week as well. Projected substantial completion date: Late-March 2023
Trash Enclosure Livermore Village Parking Garage: Phase 1 SURFACE IMPROVEMENTS | Livermore Village Parking Lot | Construct Trash Enclosure and re-pave surface adajcent surface lot in preparation for L-Street Garage construction | WestCal | February 28 | March 13 | Designated access route will be closed No delivery access to backside of businesses Revised garbage pickup location Pedestrian Detours Loss of Parking Spaces | Contractor plans to begin work outside the fenced area next week starting on 2/28/23 This work includes repaving surface lot and installation of new street lights and planter areas Contract allows a total of 10-days for this work Businesses will be notified starting today 2/22/23 Contractor meeting with Livermore Sanitation this morning to coordinate revised pickup location
L-Street Garage Livermore Village Parking Garage: Phase 2 | Livermore Village Veterans Way and S L Street | Construct new L-Street Garage on the corner of S L Street and Veterans Way | Zovich | Projected March 2023 | TBD | Pedestrian Detours Loss of Parking Spaces Long Term Road Closures | Tentative NTP date 3/6/26 Contractor continues to work on Submittals, RFIs, and required construction permits
Livermore Legacy NORTH | First Street / S L Street / Railroad Ave / S M Street | Livermore Legacy Apartments Frontage Improvements | Legacy / SBI | 2021 | TBD | Long term sidewalk closure on First Street and Occational same day lane closure on S L Street and RR Ave Full closure of S M Street for construction of new pavement - (2-3 weeks) Right lane closure on EB Railroad Ave. and Power outage during PG&E tie in work on evening of 2/25/23 | Legacy NORTH contractor plans on opening the ramp at the SW corner of RR Ave. and S L Street by 2/24. Pedestrians will be able to use all the crosswalks in that intersection. Sidewalk on RR Ave scheduled to re-opened by first week of March. Contractor will begin grading work for the flex zone area and sidewalk on First St. next week First Street sidewalk expected to be open to public by early April, this will include the crosswalk crossing S L Street Construction of sidewalk and, curb and gutter on the EAST side of S M Street is still ongoing. Contractor will begin working on the S M Street Pavement at the beginning of March. This work will require a full closure of the road (see impacts) PGE scheduled to perform tie-in work on RR Ave. on 2/25/23 (NIGHT). Pre-con scheduled for Thursday 2/23 PGE/Legacy will not be able to provide backup power during this shutdown In response to Downtown Inc.'s concerns, City will be posting DOWNTOWN PATRONS ONLY/ NO CONSTRUCTION PARKING signs in the parking area on the SW corner of Livermore Village Legacy Contractor will also supplement with their own sign
Livermore Legacy SOUTH | First Street - From S L Street to S M Street (South side) | First Street streetscape improvements | Legacy / Goodfellow Bros | 2019 | End of Feb 2023 | Loss of single parking spaces - Only as needed | Project is substantially complete and contractor just working on minor punchlist items. Contractor completed installation of the trellis downlights and performing general cleaning of the site and building storefronts last week.
Encroachment Permit No. EN220465 Comcast | Livermore Village Parking Lot | Install new service line behind downtown establishements (north side) | Comcast / Sefnco | January 20, 2023 | End of March (For all other Comcast Work noted that is not assoociated with this permit) | Pedestrian Detours Loss of Parking Spaces | Installation work completed. Restoration of the gravel parking area between the alley way and S L Street completed. *Comcast tentatively scheduled to install private portion of the run on 2/28/23 - Not part of this permit *Comcast has applied for the permit to install laterals to each building - start date TBD
CalWater Water Line Replacement | First Street - Alley between Murphy's Paw amd Caratti Jewlers; 2nd Street between K and L; K Street between 1st and 3rd; J Street between 1st and 2nd | Water main replacement | CalWater | Mid March 2023 | Early April | Lane Closures Pedestrian Detours Loss of Parking Spaces in Downtown Core Area | CWS eliminated the main replacement in the downtown alley way from the scope of this permit. Permit work for other locations in downtown core has not been issued. CWS continues to work with City regardin impacts and Traffic Control.
Underground Tank Removal | Parking Lot north of La Botica | Remove Underground Tank that was discovered first week of January | Pangea | 2nd week of February | 4th week of February | Pedestrian Detours and Loss of About 20 parking spaces for this entire week behind Plucked Chicken and Caratti Jewlers | Tank was removed last week. Test results from sampling the soils under the tank were sent over to LPFD last week for county review. Still waiting for their approval to backfill Parking area behind businesses remains closed for public safety. Businesses were notified last week about the delay.
Encroachment Permit No. EN230052 Potholing for Utilities on L Street | East sidewalk on L Street south of Veteran's Way | Pothole for Utilities | Kier and Wright and Subconsultant | 2/8/23 | 2/9/23 | Right lane closure on NB S L Street | Work and restoration was completed last week
Encroachment Permit No. EN230004 AT&T | First Street / S J Street | Replace/Splice Fiber Cable | AT&T | TBD | TBD | Loss of Parking Spaces on First Street and S J Street | Permit Issued - Waiting for AT&T to schedule pre-con and provide tentative start date.
Encroachment Permit No. EN230078 CalWater | First Street - Alley between Murphy's Paw amd Caratti Jewlers | Cap existing 4" Water line main | CalWater | 2/21/23 | 2/27/23 | Loss of Parking spaces in alley way for 1 day. Water service shut off to businesses during off hours | (Daytime and Nighttime Work) Night time work to cap existing line completed Restoration 2/27 - daytime Access through Alley way shall be maintained during construction work

## 2-14-23
UPDATED: 2/14/23
PROJECT NAME | LOCATION | DESCRIPTION | AGENCY/ CONTRACTOR/ DEVELOPER | SCHEDULED START | SCHEDULED FINISH | IMPACTS | UPDATES
Trash Enclosure Livermore Village Parking Garage: Phase 1 | Livermore Village Parking Lot | Construct Trash Enclosure and re-pave surface adajcent surface lot in preparation for L-Street Garage construction | WestCal | August 2022 | Late March 2023 | Pedestrian Detours Loss of Parking Spaces | Contractor mainly working on CMU Walls - they are currently on their 3nd week. Work is scheduled to take 3-4 weeks total. Contractor will start tomnorrow (2/15) the demo of the recently constructed sidewalk and ramp east of the fenced area. Sidewalk and ramps were not built per plan and needs to be corrected. Projected substantial completion date: Late-March 2023
Trash Enclosure Livermore Village Parking Garage: Phase 1 SURFACE IMPROVEMENTS | Livermore Village Parking Lot | Construct Trash Enclosure and re-pave surface adajcent surface lot in preparation for L-Street Garage construction | WestCal | Mid March 2023 | Late March 2023 | Pedestrian Detours Loss of Parking Spaces | Due to weather impacts - Work outside of fenced area has been pushed out until early March 2023
L-Street Garage Livermore Village Parking Garage: Phase 2 | Livermore Village Veterans Way and S L Street | Construct new L-Street Garage on the corner of S L Street and Veterans Way | Zovich | Projected March 2023 | TBD | Pedestrian Detours Loss of Parking Spaces Long Term Road Closures | Tentative NTP date 3/6/26 Contractor continues to work on Submittals, RFIs, and required construction permits
Livermore Legacy NORTH | First Street / S L Street / Railroad Ave / S M Street | Livermore Legacy Apartments Frontage Improvements | Legacy / SBI | 2021 | TBD | Same Day RIGHT lane closure at SW corner of RR Ave. and S L Street for sidewalk and ramp concrete pour on Friday 2/17/23 Long term sidewalk closure on First Street and Occational same day lane closure on S L Street and RR Ave Full closure of S M Street for construction of new pavement - (2-3 weeks) Right lane closure on EB Railroad Ave. and Power outage during PG&E tie in work on evening of 2/25/23 Shifting lane closures on S L Street to lower existing interconnect/Fiber Optics conduits crossing S L Street | Legacy NORTH Contractor to pour back on Friday 2/17/23 revised sidewalk and ramp on the SW corner of Railroad Ave. and S L Street and ramp for Veterans Way crosswalk. New Railroad Ave. sidewalk, including all crosswalks at this intersection, expected to be re-opened by first week of March. Contractor completed electrical and utility work on First Street and will begin curb and gutter construction next week First Street sidewalk expected to be open to public by early April, this will include the crosswalk crossing S L Street Construction of sidewalk and, curb and gutter on the EAST side of S M Street is ongoing. Contractor will begin working on the S M Street Pavement at the beginning of March. This work will require a full closure of the road (see impacts) PGE scheduled to perform tie-in work on RR Ave. on 2/25/23 (NIGHT). City has informed PG&E that a precon is required before the scheduled work date PGE sent out notifications to affected residents and businesses last week 2/8/23 (I need to confirm). PGE/Legacy will not be able to provide backup power during this shutdown In response to Downtown Inc.'s concerns, City will be posting DOWNTOWN PATRONS ONLY/ NO CONSTRUCTION PARKING signs in the parking area on the SW corner of Livermore Village Legacy Contractor will also supplement with their own sign
Livermore Legacy SOUTH | First Street - From S L Street to S M Street (South side) | First Street streetscape improvements | Legacy / Goodfellow Bros | 2019 | End of Feb 2023 | Loss of Parking Spaces - Will only take spaces required for trellis area they are working on that day | Contractor currently working on installation of the trellis downlights up to mid next week. Contractor completed the raising of a monument in the middle of First Street and S M Street on Monday 2/13/23
Encroachment Permit No. EN220465 Comcast | Livermore Village Parking Lot | Install new service line behind downtown establishements (north side) | Comcast / Sefnco | January 20, 2023 | Mid February | Pedestrian Detours Loss of Parking Spaces | Installation work completed. Restoration of the gravel parking area between the alley way and S L Street completed. *Comcast tentatively scheduled to install private portion of the run on 2/22/23 - Not part of this permit *Comcast has plans to install laterals to each building - to provide City with plan by end of the month - Could potentially be added to this permit
CalWater Water Line Replacement | First Street - Alley between Murphy's Paw amd Caratti Jewlers; 2nd Street between K and L; K Street between 1st and 3rd; J Street between 1st and 2nd | Water main replacement | CalWater | Mid March 2023 | Early April | Lane Closures Pedestrian Detours Loss of Parking Spaces in Downtown Core Area | CWS eliminated the main replacement in the downtown alley way from the scope of this permit. Permit work for other locations in downtown core has not been issued. CWS continues to work with City regardin impacts and Traffic Control.
Underground Tank Removal | Parking Lot north of La Botica | Remove Underground Tank that was discovered first week of January | Pangea | 2nd week of February | 2nd week of February | Pedestrian Detours and Loss of About 20 parking spaces for this entire week behind Plucked Chicken and Caratti Jewlers | Tank was removed last week. Test results from sampling the soils under the tank were sent over to LPFD last week for county review. Still waiting for their approval to backfill Parking area behind businesses remains closed for public safety. Businesses were notified last week about the delay.
Encroachment Permit No. EN230052 Potholing for Utilities on L Street | East sidewalk on L Street south of Veteran's Way | Pothole for Utilities | Kier and Wright and Subconsultant | 2/8/23 | 2/9/23 | Right lane closure on NB S L Street | Work and restoration was completed last week
Encroachment Permit No. EN230004 AT&T | First Street / S J Street | Replace/Splice Fiber Cable | AT&T | TBD | TBD | Loss of Parking Spaces on First Street and S J Street | Permit Issued - Waiting for AT&T to schedule pre-con and provide tentative start date.
Encroachment Permit No. EN230078 CalWater | First Street - Alley between Murphy's Paw amd Caratti Jewlers | Cap existing 4" Water line main | CalWater | 2/21/23 | 2/22/23 | Loss of Parking spaces in alley way for 2 days. Water service shut off to businesses during off hours | (Daytime and Nighttime Work) CWS will be notifying this week the businesses affected by the service shut off and will be posting no parking signs in the alley way. Alley way shall remain open during construction work Cappng work will be performed at night on 2/21/23 - After businesses close Prep work 2/21 - daytime Restoration 2/22 - daytime

## 2-7-23
UPDATED: 2/7/23
PROJECT NAME | LOCATION | DESCRIPTION | AGENCY/ CONTRACTOR/ DEVELOPER | SCHEDULED START | SCHEDULED FINISH | IMPACTS | UPDATES
Trash Enclosure Livermore Village Parking Garage: Phase 1 | Livermore Village Parking Lot | Construct Trash Enclosure and re-pave surface adajcent surface lot in preparation for L-Street Garage construction | WestCal | August 2022 | Late March 2023 | Pedestrian Detours Loss of Parking Spaces | Contractor mainly working on CMU Walls - they are currently on their 2nd week. Work is scheduled to take 3-4 weeks total. PGE took no exceptions to the "at Risk" section of the electrical conduits installed in this project Constructed sidewalk and ramp outside the fenced area needs to be corrected. Expect contractor to back out there to remove and replace. No tentative schedule at this time Projected substantial completion date: Late-March 2023
Trash Enclosure Livermore Village Parking Garage: Phase 1 SURFACE IMPROVEMENTS | Livermore Village Parking Lot | Construct Trash Enclosure and re-pave surface adajcent surface lot in preparation for L-Street Garage construction | WestCal | Mid March 2023 | Late March 2023 | Pedestrian Detours Loss of Parking Spaces | Due to weather impacts - Work outside of fenced area has been pushed out until early March 2023
L-Street Garage Livermore Village Parking Garage: Phase 2 | Livermore Village Veterans Way and S L Street | Construct new L-Street Garage on the corner of S L Street and Veterans Way | Zovich | Projected March 2023 | TBD | Pedestrian Detours Loss of Parking Spaces Long Term Road Closures | Tentative NTP date 3/6/23 Contractor continues to work on Submittals, RFIs, and required construction permits
Livermore Legacy NORTH | First Street / S L Street / Railroad Ave / S M Street | Livermore Legacy Apartments Frontage Improvements | Legacy / SBI | 2021 | TBD | All day RIGHT lane closure at SW corner of RR Ave. and S L Street for sidewalk and ramp construction - Through Friday 2/10/23 Long term sidewalk closure on First Street and Occational same day lane closure on S L Street and RR Ave Full closure of S M Street for construction of new pavement - (2-3 weeks) Power outage during PG&E tie in work | Legacy NORTH Contractor working on revising the sidewalk and ramp on the SW corner of Railroad Ave. and S L Street. For safety reasons, due to the elevation of the drop off, a right lane closure on EB RR Ave and SB S L Street will be in place in the vicinity of that turn. New Railroad Ave. sidewalk, including all crosswalks at this intersection, expected to be re-opened by end of February. This tentative date is dependent on PGE completing tie-in work (see below). First Street sidewalk expected to be open to public by early April, this will include the crosswalk crossing S L Street Construction of sidewalk and, curb and gutter on the EAST side of S M Street is ongoing. Contractor will begin working on the S M Street Pavement at the beginning of March. This work will require a full closure of the road (see impacts) Contractor continues to work on electrical work on RR Ave., S L Street, and First Street. - Installing conduits and pulling wire. PGE still tenatively scheduled to perform tie-in work on RR Ave. on 2/25/23 (NIGHT). PGE will be sending out notifications to affected residents and businesses tomorrow 2/8/23. PGE/Legacy will not be able to provide backup power during this shutdown
Livermore Legacy SOUTH | First Street - From S L Street to S M Street (South side) | First Street streetscape improvements | Legacy / Goodfellow Bros | 2019 | End of Feb 2023 | Loss of Parking Spaces - Will only take spaces required for trellis area they are working on that day Lane shifts on first street and S M Street | Contractor will begin installation of the downlights starting tomorrow 2/8/23 through 2/21/23 Contractor will raise a monument in the middle of First Street and S M Street on Monday 2/13/23 (see impacts)
Encroachment Permit No. EN220465 Comcast | Livermore Village Parking Lot | Install new service line behind downtown establishements (north side) | Comcast / Sefnco | January 20, 2023 | Mid February | Pedestrian Detours Loss of Parking Spaces | Installation work completed. City will be meeting this week with contractor to discuss restoration Restoration tentatively scheduled for next week during the day. *Comcast tentatively scheduled to install private portion of the run on 2/22/23 - Not part of this permit *Comcast has plans to install laterals to each building - to provide City with plan by end of the month - Could potentially be added to this permit
CalWater Water Line Replacement | First Street - Alley between Murphy's Paw amd Caratti Jewlers; 2nd Street between K and L; K Street between 1st and 3rd; J Street between 1st and 2nd | Water main replacement | CalWater | Mid March 2023 | Early April | Lane Closures Pedestrian Detours Loss of Parking Spaces in Downtown Core Area | Received a call from CWS late 2/7/23 to infrom me that they will be eliminating the main replacement in the downtown alley way from the scope of this permit. Waiting for CWS to confirm. (All updates below based on meeting with CWS prior to consideration of eliminating the work) Installation work expected to start mid March. CWS will open trench. Overall work will be 3-4 weeks with mostly NIGHT WORK CWS will possibly be in the alley way this Friday (2/10/22) to perform potholing work in preparation for trenching Alley way will remain open, No parking signs to be placed 72hrs prior. Other locations in downtown core still under review.
Underground Tank Removal | Parking Lot north of La Botica | Remove Underground Tank that was discovered first week of January | Pangea | 2nd week of February | 2nd week of February | Pedestrian Detours and Loss of About 20 parking spaces for this entire week behind Plucked Chicken and Caratti Jewlers | Tank was removed today. Waiting for test results for soils samples beneath the tank. Results due Thursday 2/9/23 If clean, pit will be backfilled and area will be paved back either Thursday or Friday If further excavation is required due to test results, contractor will secure the pit and install steel plates over the weekend
Encroachment Permit No. EN230052 Potholing for Utilities on L Street | East sidewalk on L Street south of Veteran's Way | Pothole for Utilities | Kier and Wright and Subconsultant | 2/8/23 | 2/9/23 | Right lane closure on NB S L Street | Permit was issued last week. Will begin work tomorrow Wednesday 2/8/23 Work will last for 2 days
Encroachment Permit No. EN230004 AT&T | First Street / S J Street | Replace/Splice Fiber Cable | AT&T | TBD | TBD | Loss of Parking Spaces on First Street and S J Street | Permit Issued - Waiting for AT&T to schedule pre-con and provide tentative start date.

## 2-1-23
UPDATED: 2/1/23
PROJECT NAME | LOCATION | DESCRIPTION | AGENCY/ CONTRACTOR/ DEVELOPER | SCHEDULED START | SCHEDULED FINISH | IMPACTS | UPDATES
Trash Enclosure Livermore Village Parking Garage: Phase 1 | Livermore Village Parking Lot | Construct Trash Enclosure and re-pave surface adajcent surface lot in preparation for L-Street Garage construction | WestCal | August 2022 | Late March 2023 | Pedestrian Detours Loss of Parking Spaces | Contractor continues to work on CMU Walls - will take 2-3 weeks of work remaining. Contractor also working on plumbing for fire protection. Projected substantial completion date: Late-March 2023
Trash Enclosure Livermore Village Parking Garage: Phase 1 SURFACE IMPROVEMENTS | Livermore Village Parking Lot | Construct Trash Enclosure and re-pave surface adajcent surface lot in preparation for L-Street Garage construction | WestCal | Mid March 2023 | Late March 2023 | Pedestrian Detours Loss of Parking Spaces | Due to weather impacts - Work outside of fenced area has been pushed out until early March 2023
L-Street Garage Livermore Village Parking Garage: Phase 2 | Livermore Village Veterans Way and S L Street | Construct new L-Street Garage on the corner of S L Street and Veterans Way | Zovich | Projected March 2023 | TBD | Pedestrian Detours Loss of Parking Spaces Long Term Road Closures | Tentative Notice To Proceed date 3/6/26 Contractor continues to work on Submittals, RFIs, and required construction permits
Livermore Legacy NORTH | First Street / S L Street / Railroad Ave / S M Street | Livermore Legacy Apartments Frontage Improvements | Legacy / SBI | 2021 | TBD | Same day RIGHT lane closure on RR Ave. for sidewalk and ramp demo and construction - 2/6 to 2/13 (see updates next column) Long term sidewalk closure on First Street and Occational same day lane closure on S L Street and RR Ave | Legacy NORTH Contractor will begin demoliton of the existing sidewalk and ramp on the SW corner of Railroad Ave. and S L Street. New Railroad Ave. sidewalk, including all crosswalks at the Railroad/L intersection, expected to be re-opened by end of February. This tentative date is dependent on PGE completing tie-in work (see below). Continue construction of Sidewalk and curb and gutter on the EAST side of S M Street. Installation of electrical conduits and irrigations sleeves to begin next week. Electrical work on RR Ave., S L Street, and First Street. - Installing conduits and pulling wire. AT&T completed last week the relocation of their line that conflicts with the First Street improvements. PGE still tenatively scheduled to perform tie-in work on RR Ave. on 2/25/23 (NIGHT). City Staff continues to work with PG&E and Legacy regarding minimizing impacts
Livermore Legacy SOUTH | First Street - From S L Street to S M Street (South side) | First Street streetscape improvements | Legacy / Goodfellow Bros | 2019 | TBD | Loss of Parking Spaces - Will only take spaces required for trellis area they are working on that day Pedestrian Detour crossing S M Street when working on 4-post trellis at the SE corner of 1st and S M | Contractor started work on 4-post trellis - scheduled to be compelte this week. Landscaping 120-day maintenance ongoing. Downlighting installation tenatively scheduled for 1st or 2nd week of Feb.
Encroachment Permit No. EN220465 Comcast | Livermore Village Parking Lot | Install new service line behind downtown establishements (north side) | Comcast / Sefnco | January 20, 2023 | February 4, 2023 | NIGHT WORK Pedestrian Detours Loss of Parking Spaces (between 7PM-3:30AM) | NIGHT WORK (7pm to 3AM) Started work evening of 1/23/23 Started open trench installation last night 1/31/23 Open trench is from West side of First St Ale House to S L Street. Open trench work to be completed this week. Restoration will be done the following week during day time. No Parking signs posted - Impacted businesses were personally notified Comcast contractor and City Staff will continue to notify impacted businesses and Downtown inc.
CalWater Water Line Replacement | First Street - Alley between Murphy's Paw amd Caratti Jewlers; 2nd Street between K and L; K Street between 1st and 3rd; J Street between 1st and 2nd | Water main replacement | CalWater | TBD | TBD | Lane Closures Pedestrian Detours Loss of Parking Spaces in Downtown Core Area | City staff will issue separate permit for portion of work located in the vicinity of the L-Street garage to avoid any schedule conflicts with the garage construction Still waiting on CWS to submit TCP revisions for the rest of the locations in the downtown area Overall work will be 3-4 weeks with some NIGHT WORK
Underground Tank Removal | Parking Lot north of La Botica | Remove Underground Tank that was discovered first week of January | Pangea | 2nd week of February | 2nd week of February | Pedestrian Detours Loss of About 20 parking spaces | Fire Department permit application currently being processed. Tank removal scheduled for 2/6/23
Encroachment Permit No. EN230052 Potholing for Utilities on L Street | East sidewalk on L Street south of Veteran's Way | Pothole for Utilities | Kier and Wright and Subconsultant | TBD | TBD | Shut down sidewalk and close down one northbound lane | Permit was issued last week. Tentative start date 2/7/23 Contractor to schedule precon
Encroachment Permit No. EN230004 AT&T | First Street / S J Street | Replace/Splice Fiber Cable | AT&T | TBD | TBD | Loss of Parking Spaces on First Street and S J Street | Permit Issued - Waiting for AT&T to schedule pre-con and provide tentative start date.

## 1-25-23
UPDATED: 1/25/23
PROJECT NAME | LOCATION | DESCRIPTION | AGENCY/ CONTRACTOR/ DEVELOPER | SCHEDULED START | SCHEDULED FINISH | IMPACTS | UPDATES
Trash Enclosure Livermore Village Parking Garage: Phase 1 | Livermore Village Parking Lot | Construct Trash Enclosure and re-pave surface adajcent surface lot in preparation for L-Street Garage construction | WestCal | August 2022 | March 2023 | Pedestrian Detours Loss of Parking Spaces | Mainly working on JT/Electrical conduits. PGE inspected at-risk conduits. CMU wall construction strarted this week - will take 3-4 weeks to complete Projected substantial completion date: Late-March 2023
Trash Enclosure Livermore Village Parking Garage: Phase 1 SURFACE IMPROVEMENTS | Livermore Village Parking Lot | Construct Trash Enclosure and re-pave surface adajcent surface lot in preparation for L-Street Garage construction | WestCal | January 17, 2023 | January 30, 2023 | Pedestrian Detours Loss of Parking Spaces | Due to weather impacts - Work outside of fenced area has been pushed out until Mid Feb 2023
L-Street Garage Livermore Village Parking Garage: Phase 2 | Livermore Village Veterans Way and S L Street | Construct new L-Street Garage on the corner of S L Street and Veterans Way | Zovich | Projected March 2023 | TBD | Pedestrian Detours Loss of Parking Spaces Long Term Road Closures | Tentative NTP date 3/6/26 Contractor continues to work on Submittals, RFIs, and required construction permits
Livermore Legacy NORTH | First Street / S L Street / Railroad Ave / S M Street | Livermore Legacy Apartments Frontage Improvements | Legacy / SBI | 2021 | TBD | Long term sidewalk closure on First Street and Occational same day lane closure on S L Street and RR Ave | Legacy NORTH Contractor poured remaining sidewalk and driveway on S L Street and street light foundations installations on RR Ave. Construction of Sidewalk and curb and gutter on the EAST side of S M Street has started. Installation of electrical conduits and irrigations sleeves to follow. Electrical contractor working in coodination with AT&T to relocate their line running along 1st street improvements. Existing location conflicts with curb and gutter. PGE still tenatively scheduled to perform tie-in work on RR Ave. on 2/4/23. City Staff continues to work with PG&E and Legacy regarding impact and conditions - This includes providing temporary power to impacted residents and businesses Storefront work along 1st Street has started
Livermore Legacy SOUTH | First Street - From S L Street to S M Street (South side) | First Street streetscape improvements | Legacy / Goodfellow Bros | 2019 | TBD | Loss of Parking Spaces - Will only take spaces required for trellis area they are working on that day Pedestrian Detour crossing S M Street when working on 4-post trellis at the SE corner of 1st and S M | Contractor has will continue work on single post trellis installation in flex zone. Tentatively will begin work on 4-post trellis on Thursday or Friday and continueing til next week - this will require a pedestrain detour (see impact) Landscaping is under 120-day maintenance which ends on 1/27/23 Downlighting installation tenatively scheduled for 1st week of Feb
Encroachment Permit No. EN220465 Comcast | Livermore Village Parking Lot | Install new service line behind downtown establishements (north side) | Comcast / Sefnco | January 20, 2023 | February 2, 2023 | NIGHT WORK Pedestrian Detours Loss of Parking Spaces (between 7PM-3:30AM) | NIGHT WORK (7pm to 3AM) Started work evening of 1/23/23 Completed installation (boring) between Sunrise Mountain Sports and First Street Ale House last night 1/24/23 Open trench installation will begin on 1/31/23 evening Open trench from West side of First St Ale House to S L Street. 2-3 Working Days/Nights to complete open trench installation No Parking signs posted - Impacted businesses were personally notified Comcast contractor and City Staff will continue to notify impacted businesses and Downtown inc.
CalWater Water Line Replacement | First Street - Alley between Murphy's Paw amd Caratti Jewlers; 2nd Street between K and L; K Street between 1st and 3rd; J Street between 1st and 2nd | Water main replacement | CalWater | TBD | TBD | TBD | Permit has not been issued - waiting for Calwater to submit minor plan revisions to address City comments.
Underground Tank Removal | Parking Lot north of La Botica | Remove Underground Tank that was discovered first week of January | Pangea | 2nd week of February | 2nd week of February | Pedestrian Detours Loss of About 20 parking spaces | Exposed tank, took samples, submitting permits to Alameda County and Fire Department, plated area and will remove tank when permits obtained in early February
Potholing for Utilities on L Street | East sidewalk on L Street south of Veteran's Way | Pothole for Utilities | Kier and Wright and Subconsultant | TBD | TBD | Shut down sidewalk and close down one northbound lane | Work is being scheduled for late January or early February
Encroachment Permit No. EN230004 AT&T | First Street / S J Street | Replace/Splice Fiber Cable | AT&T | TBD | TBD | Loss of Parking Spaces on First Street and S J Street | Permit Issued - Construction Crew emailed AT&T to remind them to schedule Pre-con before work can begin

## 1-18-23
UPDATED: 1/18/23
PROJECT NAME | LOCATION | DESCRIPTION | AGENCY/ CONTRACTOR/ DEVELOPER | SCHEDULED START | SCHEDULED FINISH | IMPACTS | UPDATES
Trash Enclosure Livermore Village Parking Garage: Phase 1 | Livermore Village Parking Lot | Construct Trash Enclosure and re-pave surface adajcent surface lot in preparation for L-Street Garage construction | WestCal | August 2022 | March 2023 | Pedestrian Detours Loss of Parking Spaces | Resumed Sanitary Sewer Work this week but will put on hold again to focus on JT/Electrical conduits for this week and next- PGE scheduled to inspect work 1/24-25/2023 Potentially start work on CMU walls this week
Trash Enclosure Livermore Village Parking Garage: Phase 1 SURFACE IMPROVEMENTS | Livermore Village Parking Lot | Construct Trash Enclosure and re-pave surface adajcent surface lot in preparation for L-Street Garage construction | WestCal | January 17, 2023 | January 30, 2023 | Pedestrian Detours Loss of Parking Spaces | Due to weather impacts - Work outside of fenced area has been pushed out until Feb 2023
L-Street Garage Livermore Village Parking Garage: Phase 2 | Livermore Village Veterans Way and S L Street | Construct new L-Street Garage on the corner of S L Street and Veterans Way | Zovich | Projected March 2023 | TBD | Pedestrian Detours Loss of Parking Spaces Long Term Road Closures | Pre-con held 1/18/23 Tentative NTP date 3/6/26 Contractor continues to work on Submittals, RFIs, and required construction permits
Livermore Legacy NORTH | First Street / S L Street / Railroad Ave / S M Street | Livermore Legacy Apartments Frontage Improvements | Legacy / SBI | 2021 | TBD | Long term sidewalk closure on First Street and Occational same day lane closure on S L Street and RR Ave | Legacy Contractor will resume their work on the S L Street sidewalk this week - Forms this week - pour next week Begin street light foundations installations on RR Ave. Will work begin work on AT&T line relocation on First Street next week - 1/23 Storefront work on First St – End of month tentative PGE scheduled tie-in 2/4/23 – Permit not issued – waiting for address list - City has asked Legacy to help push PGE to provide this list
Livermore Legacy SOUTH | First Street - From S L Street to S M Street (South side) | First Street streetscape improvements | Legacy / Goodfellow Bros | 2019 | March 2023 | None | Trellis Work completed. Working on punchlist and project Closeout
Encroachment Permit No. EN220465 Comcast | Livermore Village Parking Lot | Install new service line behind downtown establishements (north side) | Comcast / Sefnco | January 20, 2023 | February 2, 2023 | Pedestrian Detours Loss of Parking Spaces | Working on Final Puch
CalWater Water Line Replacement | First Street - Alley between Murphy's Paw amd Caratti Jewlers and other locations | Water main replacement | CalWater | TBD | TBD | TBD | Permit has not been issued - waiting for Calwater to submit minor plan revisions to address City comments.
Underground Tank Removal | Parking Lot north of La Botica | Remove Underground Tank that was discovered first week of January | Pangea | 2nd week of February | 2nd week of February | Pedestrian Detours Loss of About 20 parking spaces | Exposed tank, took samples, submitting permits to Alameda County and Fire Department, plated area and will remove tank when permits obtained in early February
Potholing for Utilities on L Street | East sidewalk on L Street south of Veteran's Way | Pothole for Utilities | Kier and Wright and Subconsultant | TBD | TBD | Shut down sidewalk and close down one northbound lane | Work is being scheduled for late January or early February
Encroachment Permit No. EN230004 AT&T | First Street / S J Street | Replace/Splice Fiber Cable | AT&T | TBD | TBD | Loss of Parking Spaces on First Street and S J Street | Permit Issued - Construction Crew emailed AT&T to remind them to schedule Pre-con before work can begin

## 1-11-23
UPDATED: 1/11/23
PROJECT NAME | LOCATION | DESCRIPTION | AGENCY/ CONTRACTOR/ DEVELOPER | SCHEDULED START | SCHEDULED FINISH | IMPACTS | UPDATES
Trash Enclosure Livermore Village Parking Garage: Phase 1 | Livermore Village Parking Lot | Construct Trash Enclosure and re-pave surface adajcent surface lot in preparation for L-Street Garage construction | WestCal | August 2022 | March 2023 | Pedestrian Detours Loss of Parking Spaces | Ready to begin CMU wall construction and continue SS installation - depending on weather Waiting on PQR regarding modifications to JT/Electrical conduits - PGE scheduled to inspect work 1/24-25/2023
Trash Enclosure Livermore Village Parking Garage: Phase 1 SURFACE IMPROVEMENTS | Livermore Village Parking Lot | Construct Trash Enclosure and re-pave surface adajcent surface lot in preparation for L-Street Garage construction | WestCal | January 17, 2023 | January 30, 2023 | Pedestrian Detours Loss of Parking Spaces | Scheduled to begin working on surface improvements outside the fenced area on Jan 17, 2023 - depending on weather
L-Street Garage Livermore Village Parking Garage: Phase 2 | Livermore Village Veterans Way and S L Street | Construct new L-Street Garage on the corner of S L Street and Veterans Way | Zovich | Projected March 2023 | TBD | Pedestrian Detours Loss of Parking Spaces Long Term Road Closures | Pre-con scheduled for 1/19/23 Contractor starting to provide submittals
Livermore Legacy NORTH | First Street / S L Street / Railroad Ave / S M Street | Livermore Legacy Apartments Frontage Improvements | Legacy / SBI | 2021 | TBD | Long term sidwwalk and lane closures Occational same day lane closures | 1st street improvement work on hold due to weather Will work on UG utilities – AT&T, Interconnect, SL once weather permitting PGE scheduled tie-in 2/4/23 – Permit not issued – waiting for address list Storefront work on First St – End of month tentative
Livermore Legacy SOUTH | First Street - From S L Street to S M Street (South side) | First Street streetscape improvements | Legacy / Goodfellow Bros | 2019 | TBD | Loss of Parking Spaces | Installation of trellis tops currently on hold due to weather. Contractor expects a window of clear weather in late January and will resume work. Landscaping is under 120-day maintenance which ends on 1/27/23
Encroachment Permit No. EN220465 Comcast | Livermore Village Parking Lot | Install new service line behind downtown establishements (north side) | Comcast / Sefnco | January 20, 2023 | February 2, 2023 | Pedestrian Detours Loss of Parking Spaces | Pre-Con scheduled for 1/12/23 Begin notification today 1/11/23 Night Work Will begin work on the east end next to Trash enclosure and work towards the west
CalWater Water Line Replacement | First Street - Alley between Murphy's Paw amd Caratti Jewlers |  | CalWater | TBD | TBD